STATEMENT OF WORK

Confidential — Between the Parties Named Below

TPE COMMUNICATION SYSTEM

A unified, multi-audience, multi-channel, template-driven communicationengine for the Indian insurtech secondary market

| 49 Lifecycle Triggers | 5 Audiences | 4 Channels | 25 Engineering Days (Core) |
| --- | --- | --- | --- |

BETWEEN

| THE CLIENT | THE CONSULTANT |
| --- | --- |
| Fairvalue Insuretech Pvt. Ltd. (operating as “The Policy Exchange”) Registered office: Noida, Uttar Pradesh, India CIN: [Client to insert] (“Client” / “TPE”) | Ashish Kumar Satyam Principal Engineer & Solution Architect Independent Consultant, BFSI & Insurtech PAN / GSTIN: [Consultant to insert] (“Consultant”) |

Document ID: TPE-COMMS-SOW-2026-001  |  Version 3.0  |  Effective Date: 26 April 2026

Classification: Internal & Confidential — Distribution per Section 4

# Table of Contents

Fifty-five sections in thirteen thematic parts. Read in order; each part terminates in an independently consumable artefact (delivery), gate (governance), or commitment (commercial / legal).

|  | PART I — DOCUMENT CONTROL & EXECUTIVE |
| --- | --- |
| 1 | Document Information |
| 2 | Document Control & Approval Matrix |
| 3 | Version History |
| 4 | Distribution List |
| 5 | Executive Summary |
| 6 | Executive Dashboard |
| 7 | Business Case & ROI Analysis |
|  | PART II — CONTEXT & SCOPE |
| 8 | Business Context — The Policy Exchange |
| 9 | Problem Statement & Current State |
| 10 | Project Vision, Objectives & Success Metrics |
| 11 | Scope (In / Out) |
|  | PART III — STAKEHOLDERS & AUDIENCE |
| 12 | Stakeholder Register |
| 13 | Audience Architecture (5 audiences) |
|  | PART IV — DOMAIN MODEL |
| 14 | Trigger Catalogue (49 triggers) |
| 15 | Channel Strategy |
|  | PART V — SOLUTION |
| 16 | Template Management — Architectural Pillar |
| 17 | Solution Architecture (3 pillars) |
| 18 | Skill Catalogue (Claude Code surface) |
|  | PART VI — COMPLIANCE, SECURITY & QUALITY |
| 19 | Compliance & Regulatory Layer |
| 20 | Security & Privacy Framework |
| 21 | Quality Assurance & Testing Strategy |
|  | PART VII — DELIVERY |
| 22 | Implementation Phases & Timeline |
| 23 | Deliverables (per phase) |
| 24 | Acceptance Criteria & Procedure |
|  | PART VIII — GOVERNANCE |
| 25 | Roles & Responsibilities (RACI) |
| 26 | Communication Management Plan |
| 27 | Change Management Process |
| 28 | Service Level Agreements |
| 29 | Governance & Review Cadence |
|  | PART IX — RISK & DEPENDENCIES |
| 30 | Assumptions |
| 31 | Dependencies |
| 32 | Risk Register |
|  | PART X — RESOURCING & READINESS |
| 33 | Effort Estimation |
| 34 | Resource Plan |
| 35 | Operational Readiness & Go-Live Criteria |
| 36 | Knowledge Transfer & Training Plan |
| 37 | Post-Implementation Support & Maintenance |
|  | PART XI — COMMERCIAL TERMS |
| 38 | Charges & Engagement Model |
| 39 | Payment Schedule & Milestones |
| 40 | Invoicing, Taxes & Out-of-Pocket Reimbursements |
| 41 | Change Orders & Rate Card |
|  | PART XII — LEGAL & CONTRACT TERMS |
| 42 | Warranty & Service Standards |
| 43 | Limitation of Liability |
| 44 | Indemnification |
| 45 | Insurance Requirements |
| 46 | Term, Renewal & Termination |
| 47 | Confidentiality, IP & Data Ownership |
| 48 | Data Protection (DPDPA) & DPA Reference |
| 49 | Force Majeure |
| 50 | Governing Law & Dispute Resolution |
| 51 | General Provisions |
|  | PART XIII — REFERENCE & SIGN-OFF |
| 52 | Glossary |
| 53 | References |
| 54 | Sign-off |

# Executive Briefing

For the Founders, CTO, Head of Compliance and Head of Customer Experience.

The Policy Exchange (“TPE”) is building an unusual asset class — pre-owned life-insurance policies — and an unusual two-sided marketplace to transact them. Every assignment creates a multi-decade communication obligation: an investor who paid the surrender value upfront must be kept current on premiums for 10 to 25 years, against the backdrop of eleven insurance partners, two regulators, and an Indian policyholder base that conducts the rest of its life over WhatsApp. The communication system this Statement of Work proposes is therefore not a marketing tool. It is operational infrastructure for a regulated, long-tail relationship business.

Concretely, the engagement will deliver a versioned content library covering forty-nine lifecycle triggers across five distinct audiences and four channels, with templates as first-class entities that move through a defined draft → review → approved → active → deprecated → archived lifecycle. A compliance lint engine will enforce DLT, IRDAI, WhatsApp BSP and DPDPA rules at the approval gate — before any message leaves the system — replacing the current spreadsheet-and-inbox approach. Authoring is owned by the Consultant in close pairing with TPE Engineering; approval authority remains with the Client’s CX, Compliance and Brand leads.

Live dispatch via MSG91, Karix or Gupshup is held to an optional Phase 5, gated on channel-provider selection and contract. Success is measured on seven baselined objectives, the most consequential of which is a target twenty-percent reduction in investor premium-default rate within six months of go-live. Core delivery is twenty-five working consultant days plus nine days of Client reviewer time, distributed across four phases that each terminate in an independently consumable artefact.

This v3.0 of the Statement of Work has been refactored from a TPE-internal artefact into a contractual SOW between Fairvalue Insuretech Pvt. Ltd. (the Client) and the Consultant. The full Commercial Terms (Part XI) and Legal & Contract Terms (Part XII) now appear in this document. We are deliberately not building a customer data store, a CRM, or an analytics dashboard — those are out of scope and routed to separate engagements as they arise. The constraint is the value: a communication system that an auditor, a regulator and an investor can all read without ambiguity.

Reading order. Parts I–II (Sections 1–11) establish document control, executive summary, context and scope. Parts III–V (12–18) define stakeholders, the domain and the solution. Part VI (19–21) covers compliance, security and quality. Part VII (22–24) is delivery. Part VIII (25–29) is governance. Parts IX–X (30–37) cover risk, resourcing and readiness. Part XI (38–41) is commercial. Part XII (42–51) is legal and contract terms. Part XIII (52–54) is glossary, references and signature.

PART I

Document Control & Executive

# 1. Document Information

This Statement of Work (“SOW”) formalises the scope, architecture, deliverables, effort, commercial terms, legal terms and acceptance criteria for the TPE Communication System. Once signed by both Parties (Section 54), it becomes the source of truth for the engagement and the brief for downstream implementation. It supersedes any prior verbal understanding.

| Document Name | TPE Communication System — Statement of Work |
| --- | --- |
| Document ID | TPE-COMMS-SOW-2026-001 |
| Version | 3.0 |
| Effective Date | 26 April 2026 |
| Engagement Type | Time-bounded fixed-scope consulting; phase-billed; T&M for change orders |
| Parties | Fairvalue Insuretech Pvt. Ltd. (“Client” / “TPE”) and Ashish Kumar Satyam (“Consultant”) |
| Author | Ashish Kumar Satyam (Consultant) |
| Counter-signatories | Founder / CTO / Head of Compliance / Head of CX (Client) |
| Status | Pending counter-signature |
| Review Cycle | Per phase gate; quarterly post go-live |
| Classification | Internal & Confidential |
| Retention | Active term + 7 years (per Income Tax / Companies Act archival requirements) |

# 2. Document Control & Approval Matrix

This section formalises ownership, review and approval of this SOW as a controlled document. Any change to scope, effort, deliverables, commercial terms or legal terms requires re-approval through the matrix below before the change takes effect. The full Change Management Process is in Section 27.

## 2.1  Approval matrix

| Role | Party | Approval scope | Mechanism |
| --- | --- | --- | --- |
| Sponsor — Founder | Client — Naveen Gupta / Safia Anwar / Tarun Bahri | Commercial terms; strategic intent; final sign-off | Wet or electronic signature on Section 54 |
| Chief Technology Officer | Client | Architecture; integrations; security posture | Electronic signature; phase-gate review |
| Head of Compliance | Client | Regulatory scope (DLT, IRDAI, DPDPA, FATCA, TDS) | Electronic signature; lint-rule sign-off |
| Head of CX | Client | Trigger catalogue; brand voice; audience map | Electronic signature; review queue |
| Engagement Lead | Consultant — Ashish Kumar Satyam | Scope decomposition; plan integrity; weekly status; deliverable quality | Owns this document; cuts new versions |

## 2.2  Document state machine

| State | Meaning | Permitted next states |
| --- | --- | --- |
| draft | Author iterating; not yet circulated | in_review, archived |
| in_review | Circulated to approvers; comments open | approved, draft (returned) |
| approved | All approvers signed; document is the engagement bible | amended (new version), archived |
| amended | Substantive change in flight; previous version retained | approved, archived |
| archived | Superseded; read-only; retained for audit | (terminal) |

## 2.3  Document version control

Version increments follow semantic-versioning conventions adapted for documents:

- MAJOR (x.0) — change in scope, deliverables, effort, commercial terms or legal terms. Requires counter-signature by all roles in 2.1.

- MINOR (3.x) — clarification, additional detail, error correction; no scope or commercial impact. Approval by Engagement Lead and one Client approver.

- PATCH (3.0.x) — typographical or formatting only. Engagement Lead authority alone.

- Every version cuts a new entry in Section 3 with rationale.

- Comments and redlines are captured in-document during in_review; final approval clears comments.

# 3. Version History

Version history is curated to substantive business-level changes. Editorial passes, formatting fixes and cosmetic refinements are tracked in the document repository, not here.

| Version | Date | Author | Substantive changes |
| --- | --- | --- | --- |
| 1.0 | 26 Apr 2026 | Consultant | Initial SOW: scope, audience map, 49-trigger catalogue, channel strategy, template-management architecture, compliance layer, phased delivery, effort estimate. |
| 1.1 | 26 Apr 2026 | Consultant | Reframed audience and approval routing for TPE-internal review; updated RACI and effort estimates. |
| 2.0 | 26 Apr 2026 | Consultant | The document expanded from 26 to 41 sections in eleven thematic parts. Fifteen new sections added across governance (Approval Matrix, Distribution List, Stakeholder Register, Communication Plan, Change Management, SLA, Resource Plan, Operational Readiness, Knowledge Transfer, Post-Implementation Support) and assurance (Security & Privacy, QA & Testing, Confidentiality & IP). Risks expanded into a full Risk Register. |
| 3.0 | 26 Apr 2026 | Consultant | Reframed from internal artefact to external Consultant→Client SOW. Added Part XI Commercial Terms (charges, payment milestones, invoicing, taxes, change orders, rate card). Added Part XII Legal & Contract Terms (warranty, liability cap, indemnification, insurance, termination, governing law, dispute resolution, force majeure, DPA reference, general provisions). Tightened Acceptance (Section 24) with deemed-acceptance window and rework cap. Cleaned Distribution List and consolidated Sign-off into single counter-signature page. |

# 4. Distribution List

Classified Internal & Confidential. Distribution is restricted to the parties named below. Re-distribution, external sharing or use in external communications requires the Client Sponsor’s written approval. The Consultant will not distribute this SOW or any derivative beyond the parties listed without the Client’s prior consent.

| Recipient | Role | Format | Purpose |
| --- | --- | --- | --- |
| Client Sponsor (Founders) | Approver | DOCX + signed PDF | Approve scope; sign Section 54 |
| Client CTO | Approver | DOCX | Architecture sign-off |
| Client Head of Compliance | Approver | DOCX | Regulatory sign-off |
| Client Head of CX | Approver | DOCX | Brand and trigger sign-off |
| Client Operations Lead | Implementation owner | DOCX | Day-to-day delivery |
| Client Engineering Team | Implementation pair | DOCX | Build reference |
| Client Internal Audit (post-launch) | Reviewer | PDF (read-only) | Audit-trail evidence |
| Consultant — Engagement Lead | Author | DOCX (master) | Source of truth; controlled |
| Document repository | System of record | DOCX + PDF | Versioned archive |

# 5. Executive Summary

### Why this matters

TPE operates an unusual two-sided insurance marketplace: policyholders assign their policies to investors who then pay future premiums for 10 to 25 years until maturity. This creates a long-tail communication obligation that does not exist for standard insurers. Premium-due reminders to investors alone will dominate message volume across the next two decades. Today, content is held in spreadsheets, ad-hoc templates and individual mailboxes, with no compliance lint, no version control, no audit trail and no path to multi-language scaling.

### What this engagement delivers

A versioned content library and authoring toolkit covering 49 lifecycle triggers across five audiences (policyholder, investor, insurer partner, internal ops, regulator) and four channels (Email, SMS, WhatsApp, RCS). Templates are first-class entities with a defined lifecycle, enabling reuse, A/B variants, multi-language localisation, and a compliance lint that prevents non-compliant SMS or WhatsApp messages from shipping. The system is delivered as a Claude Code skill suite plus a structured YAML library, with optional later integration to MSG91 / Karix / Gupshup for direct dispatch.

### Quantified scope

| Dimension | v1 Scope | Steady-state |
| --- | --- | --- |
| Triggers | 49 | 60+ |
| Audiences | 5 | 5 |
| Channels | 4 | 4 + voice |
| Languages | EN, HI | EN, HI + 8 regional |
| Template count (estimate) | ~120 | 300+ |
| Unique content cells | ~600 | 3,000+ |
| Insurer partners (B2B) | 11 | 20+ |
| Compliance regimes covered | DLT, IRDAI, WhatsApp BSP, DPDPA, FATCA, TDS | + GDPR-equivalent on cross-border data |

### Effort & timeline at a glance

| P1 Foundation 5 days | ▶ | P2 PH Library 8 days | ▶ | P3 INV+INS+OPS+REG+HI 7 days | ▶ | P4 Compliance Layer 5 days | ▶ | P5 Live Dispatch (opt.) 10 days |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Core delivery (Phases 1–4): 25 working consultant-days. Phase 5 (live dispatch integration) is gated on budget and channel-provider selection and is not on the critical path for value realisation.

# 6. Executive Dashboard

Single-page snapshot for the Sponsor. Status badges show engagement readiness for each delivery dimension; metric tiles summarise what the Client is signing up for. Refreshed at every phase gate.

### Engagement readiness status

| ● Scope locked | ● Effort baselined | ● Risks cataloged | ● Compliance mapped | ● Phase 5 gated |
| --- | --- | --- | --- | --- |

### Headline metrics

| 49 Triggers | 5 Audiences | 4 Channels | 25 Eng days (core) |
| --- | --- | --- | --- |

| 9 Reviewer days | 4 Phases (core) | 6 Compliance regimes | 20% Default-rate ↓ |
| --- | --- | --- | --- |

### Phase-gate health (forecast)

| Phase | Health | Forecast outcome | Watch-item |
| --- | --- | --- | --- |
| P1 Foundation | ● L | Repo + 5 skills + PH-03 walkthrough | None — straightforward scaffolding |
| P2 PH Library | ● L | All 18 PH triggers + ~50 templates | Spreadsheet content quality |
| P3 INV+INS+OPS+REG+HI | ● M | 31 triggers; Hindi variants | Reviewer bandwidth |
| P4 Compliance Layer | ● L | 30+ lint rules; approval gate | Disclaimer text final from Compliance |
| P5 Live Dispatch | ● M | MSG91 / Karix / Gupshup; WA BSP | Channel-provider contracts (Client) |

What an approver is signing for. Twenty-five consultant-days plus nine reviewer days, four phases, an independently consumable artefact at the end of each phase, and a measurable twenty-percent target reduction in investor premium-default rate within six months of go-live. Phase 5 (live dispatch) is held separately and gated on channel-provider selection — it is not on the critical path for value realisation. Commercial terms, including total contract value and milestone payments, are in Part XI.

# 7. Business Case & ROI Analysis

Twenty-five consultant-days is the input. The outputs justifying the investment are quantified below across four dimensions: operational savings, risk reduction, revenue protection, and compounding benefit. The single largest contributor is investor premium-default-rate reduction — every percentage point preserved is lifetime-value retained on a 10–25 year stream.

## 7.1  Quantified value drivers

| Driver | Baseline | v1 Target | Annualised value |
| --- | --- | --- | --- |
| Investor premium-default rate (revenue protection) | Internal benchmark | −0% within 6 months | ₹ multi-crore — preserves multi-decade premium streams; modelled separately |
| Ops time on routine drafting (operational saving) | ≥ 2h per template | ≤ 30 min draft → approved | ≥ 20 person-hours/week saved ≈ 1,000 hrs/yr |
| Compliance-incident exposure (risk reduction) | Manual checks, ad-hoc | Lint at approval gate | Avoided fines / blocks; quantified in Risk Register Section 32 |
| Time-to-launch new audience or channel (compounding) | Weeks of bespoke work | Days, via reuse + variants | Future-state enabler — materialises in v2 / regional expansion |
| Audit reconstruction effort (risk reduction) | Days per regulator query | 100% versioned, near-zero | Material if a regulator query lands; insurance against rare events |

## 7.2  Investment vs. return summary

| Item | Quantum | Notes |
| --- | --- | --- |
| Consultant effort (P1–P4) | 25 days | Core delivery; see Section 38 for charges |
| Reviewer effort (CX + Compliance + Brand) | 9 days | Client-internal cost; spread across project |
| Phase 5 effort (gated, optional) | 10 days | Triggered only on signed Phase 5 schedule |
| Year-1 ops time saved (estimate) | ≥ 1,000 hrs | ≈ 0.5 FTE — funds onward improvements |
| Year-1 default-rate impact | −20% target | Largest single driver of NPV |
| Indicative payback period | ≤ 6 months | Default-rate impact alone clears the consulting cost |

How we frame the case. We do not claim a precise rupee NPV. Default-rate, ops-saving and incident-avoidance translate into rupees only in retrospect, with the actual numbers measured at the 6-month review (Section 10 objectives O6 and O7). The honest claim is that the targets are conservative, the baseline is the current spreadsheet-and-inbox state, and the consulting investment is small enough that even modest realisation on any one driver clears the cost.

PART II

Context & Scope

# 8. Business Context — The Policy Exchange

The Policy Exchange (“TPE”), operating under Fairvalue Insuretech Pvt. Ltd., is a Noida-headquartered insurtech founded in 2022 by Naveen Gupta, Safia Anwar and Tarun Bahri. TPE has raised approximately USD 2.49M across four rounds, including a USD 1.5M Pre-Series B (November 2025) led by VLS Finance, True Blue Holding and 1Crowd. TPE’s stated goal is to safeguard one million policyholders over the next three years.

### Two-sided business model

| Side | Customer | Value provided | Communication character |
| --- | --- | --- | --- |
| Sell-side | Policyholders unable or unwilling to continue paying premiums | Surrender value paid up-front; premium obligation transferred to investor | Empathetic, simple, reassuring; often in vernacular |
| Buy-side | Retail and HNI investors seeking stable yield (~12–14% claimed) | Access to pre-owned policies as an investable asset class | Professional, data-led, opportunity-framed; long-running for 10–25 years |
| B2B | 11 insurance carriers (Aditya Birla, Aviva, Bajaj, Bharti, Edelweiss, Generali, India First, Bandhan, Reliance, Ageas, ...) | Premium continuity; formal assignment intimation; reconciliation | Formal, structured, attachment-heavy (MIS files) |

### Adjacent products

- Loan against insurance policy — liquidity without surrender; introduces a multi-year EMI communication track.

- Maturity / claim coordination on assigned policies — TPE acts as agent between insurer and assignee investor.

- Future: re-investment products that roll matured policy proceeds into new assignments.

Why this is different from generic insurance comms. Standard carriers communicate with one party (the policyholder). TPE communicates with up to five parties about the same policy (seller, buyer, carrier, internal ops, regulator), often simultaneously, and continues investor communication for the entire remaining term of the policy — which can exceed two decades. A copy-paste-from-Gmail approach does not scale past a few hundred active policies; the operational risk (missed premium → lapsed policy → litigation from investor) grows linearly with policy count.

# 9. Problem Statement & Current State

The findings below were observed during scoping conversations with TPE Operations and CX leadership in April 2026. They constitute the baseline against which the v1 success criteria (Section 10) are measured.

### Observed today

- Communication content is maintained as informal spreadsheets and free-text drafts in individual inboxes; no canonical source of truth.

- No version history — when a copy is updated, the prior version and the rationale for the change are lost.

- No compliance lint — DLT-template-id, IRDAI mandatory disclosures, WhatsApp BSP category and opt-out footers are checked manually, if at all.

- No reuse — a generic OTP message exists in three different forms across Registration, e-Sign and Login flows.

- No multi-channel parity — the same message intent rendered in Email and WhatsApp can drift in tone, factual content and disclaimers.

- No structured cadence model — escalation rules (e.g. KYC nudge weekly × 4 then monthly × 4 then close) live in operator memory.

- No translation pipeline — Hindi or regional-language variants are produced ad-hoc per campaign.

- Limited audit trail — when a regulator or investor questions a communication, reconstructing what was sent, when, and why is non-trivial.

### Cost of the status quo

| Risk | Likely | Indicative impact |
| --- | --- | --- |
| Missed investor premium reminder → policy lapse → investor loss | High | Investor lawsuit + reputational harm + regulator scrutiny |
| Non-DLT compliant SMS → DOT block of sender ID | Medium | All transactional SMS halted across audiences for 24–72h |
| WhatsApp template miscategorised (Promotional vs Utility) | Medium | Template rejection, delivery delay, BSP fines |
| Missing IRDAI mandatory disclosure on promo material | Medium | Show-cause notice, mandatory withdrawal of campaign |
| Inconsistent tone across channels for same trigger | High | Customer confusion, increased support load |
| Lost institutional knowledge when ops staff change | High | Quality regression, longer ramp-up for new hires |

# 10. Project Vision, Objectives & Success Metrics

### Vision

Every TPE communication is authored once, approved once, rendered consistently across every channel and language, and shipped only after passing automated compliance checks — with full version history available for audit and continuous improvement.

### Measurable objectives (v1)

| # | Objective | Target metric | Baseline |
| --- | --- | --- | --- |
| O1 | Centralise communication content into a single versioned library | 100% of v1 triggers covered (49/49) | 0% |
| O2 | Eliminate manual compliance review for routine messages | ≥ 95% of templates pass auto-lint pre-review | Manual on every template |
| O3 | Reduce time to author and approve a new message | ≤ 30 minutes from draft to approved | ≥ 2 hours typical |
| O4 | Enable safe multi-language expansion | Hindi variants for 100% of PH-facing templates | Ad-hoc, partial |
| O5 | Provide audit-grade evidence of every dispatched message | 100% messages traceable to a versioned template | Reconstructed manually |
| O6 | Reduce investor premium-default rate via reliable cadence | Default-rate decline of ≥ 20% within 6 months of go-live | Current internal benchmark |
| O7 | Reduce ops-team time spent on routine drafting | Save ≥ 20 person-hours / week within 90 days of go-live | n/a |

How we measure value, not hype. Each objective has a target and a baseline. If the improvement against baseline is not evident at the 6-month review, the corresponding capability is reconsidered or removed. Vanity metrics (template count, lines of code, slash commands shipped) are explicitly out of scope for success measurement.

# 11. Scope

## 11.1  In Scope

- Trigger catalogue covering 49 lifecycle events across PH, Investor, Insurer, Internal, Regulatory audiences.

- Template Library (first-class CMS): create, version, approve, deprecate, search, link variants, render per channel, validate variables.

- Channel renderers for Email, SMS, WhatsApp (template + free text), RCS.

- Cross-cutting axes: language (EN, HI in v1), audience tone, sender identity, compliance class.

- Compliance lint engine: DLT (India SMS), IRDAI mandatory disclosures, WhatsApp BSP category, opt-out footer, time-of-day windows, transactional vs promotional separation.

- Cadence and escalation engine: per-trigger schedule rules, retry-and-close logic.

- Personalisation token library and validation.

- Claude Code skill suite (slash commands + agents) to author, preview, lint, search, export the library.

- Documentation: this SOW, runbook, template-author guide, compliance reference card.

- Acceptance test pack covering all v1 triggers and lint rules.

## 11.2  Out of Scope (v1)

- Direct dispatch to channel providers (MSG91, Karix, Gupshup, WhatsApp BSP, SMTP). Optional Phase 5 — separate signed schedule.

- Customer-data store / CRM functionality. The system consumes existing TPE data; it is not a system of record for customers.

- Real-time analytics / BI dashboards on delivery rates. Existing tools to be used.

- Voice / IVR scripting beyond brief reference notes within templates.

- Sentiment analysis or NLP-based reply handling.

- AI-generated copy at runtime. All content is human-authored and approved; AI assists during authoring only.

- Replacement of the existing MIS Pipeline (which already serves INS-02 premium remittance attachments).

PART III

Stakeholders & Audience

# 12. Stakeholder Register

The RACI (Section 25) tells you who does what on a given activity. This register tells you who cares about the engagement, how much, and what they need to keep that interest constructive. Stakeholders are listed in priority order; engagement intensity is calibrated to influence × interest.

| Stakeholder | Influence | Interest | Concerns | Engagement |
| --- | --- | --- | --- | --- |
| Founders (Sponsors) | H | H | Burn vs. impact; investor trust | Phase-gate review; weekly status |
| CTO | H | H | Architecture, integrations, tech-debt | Weekly review; phase-gate sign-off |
| Head of Compliance | H | H | Regulator exposure; lint accuracy | Continuous review queue |
| Head of CX | H | H | Brand voice; PH experience | Continuous review queue |
| Operations Lead | M | H | Day-to-day workload; tooling | Weekly working session |
| Engineering Team | M | H | Build clarity; standards | Daily standup; pair authoring |
| IRDAI (regulator) | H | L | Statutory compliance | Indirect — via Compliance Lead |
| TRAI / DLT operators | H | L | SMS template registration | Indirect — via CTO at P5 |
| Insurance partners (11) | M | M | MIS continuity; assignment SLA | Existing partner cadence; INS-02 |
| Investors (TPE customers) | L | H | Reliable premium reminders | Channelled via INV trigger flows |
| Policyholders | L | H | Empathetic, vernacular contact | Channelled via PH trigger flows |
| Internal Audit | M | L | Audit-trail quality | Documented post-launch review |

Influence × Interest = engagement intensity. High-influence + high-interest stakeholders (founders, CTO, Compliance, CX) are managed closely with weekly contact and phase-gate sign-off. High-influence + low-interest stakeholders (IRDAI, TRAI) are kept satisfied via the Compliance Lead — they should not need to interact with this engagement directly. Low-influence + high-interest (PH, INV) are the reason the engagement exists — they are served via the trigger flows, not via direct project engagement.

# 13. Audience Architecture

Five audiences each with distinct voice, channel mix, compliance regime and sender identity. Treating them uniformly is the single largest source of avoidable error in insurance communication.

Policyholder — Seller

Voice: Empathetic, simple, reassuring; never urgency-marketing; vernacular-friendly Primary channels: WhatsApp (primary), SMS, Email Compliance regime: DLT-Service / DLT-Promo, IRDAI disclosures, opt-out (DPDPA) Sender identity: TPE Customer Care

Investor — Buyer (10–25 year relationship)

Voice: Professional, data-led, returns-framed, long-time-horizon Primary channels: Email (primary), WhatsApp, RCS, SMS for OTP and dues Compliance regime: DLT-Service, IRDAI 'subject of solicitation', FATCA references Sender identity: TPE Investments

Insurance Partner — B2B (11 carriers)

Voice: Formal, structured, evidence-attached, traceable Primary channels: Email + carrier-portal upload (Excel attachments via MIS Pipeline) Compliance regime: Bilateral SLA, audit log Sender identity: TPE Operations

Internal Ops / Sales / Agents

Voice: Concise, action-oriented; surface decisions and exceptions Primary channels: Slack / Teams, Email Compliance regime: Internal information-classification policy Sender identity: TPE System Bot

Regulator / Statutory

Voice: Statutory, audit-grade, version-stamped Primary channels: Portal upload, secure email Compliance regime: IRDAI, GST, Income Tax (TDS), DPDPA Sender identity: TPE Compliance

PART IV

Domain Model

# 14. Trigger Catalogue (49 triggers)

The trigger catalogue is the system’s map of every moment we communicate. Forty-nine triggers are organised into five audience streams; each stream is presented as a single table for at-a-glance comparison across statuses, channels and cadence rules.

Each trigger has a stable identifier, one or more statuses, a channel mix and a cadence rule. Identifiers are immutable; titles may be revised in minor versions.

## 14.1  A. Policyholder Lifecycle (18 triggers)

| ID | Trigger | Statuses | Channels | Cadence |
| --- | --- | --- | --- | --- |
| PH-01 | Lead Captured | New / Contacted / Qualified / Disqualified | Email, WA | T+0,1,3,7 drip |
| PH-02 | Registration | Started / OTP Sent / Verified / Abandoned | SMS, WA, Email | Abandoned: 1h, 24h, 72h |
| PH-03 | KYC | Done / In-progress / Failed / Pending | All | Pending: 1/wk x4, 1/mo x4, close |
| PH-04 | Policy Doc Upload | Uploaded / Reviewing / Verified / Rejected | Email, WA | Per state |
| PH-05 | Policy Verification | In-progress / Verified / Discrepancy / Insurer non-response | WA, Email | Update every 48h |
| PH-06 | Surrender Value Quote | Generated / Sent / Viewed / Expired (7d) / Counter-offer | Email, WA | T+0, T+2, T+5, T-1 pre-expiry |
| PH-07 | Offer Decision | Accepted / Rejected / Negotiating / Silent | Email, WA | Silent: 3d, 7d |
| PH-08 | Assignment Paperwork | Form Gen / e-Sign Initiated / e-Sign Done / Physical / NOC | Email, WA, SMS | e-Sign: T+1, T+3 |
| PH-09 | Investor Matched | Found / Confirmed | WA, Email | Immediate |
| PH-10 | Disbursement | Initiated / In-process / Success / Failed | SMS, WA, Email | Per state |
| PH-11 | Post-Assignment Welcome | Recorded / Welcome | Email, WA | + quarterly newsletter |
| PH-12 | Loan Application | Started / Docs pending / Submitted / Under review | All | Standard |
| PH-13 | Loan Approval | Approved / Conditional / Rejected | Email, WA, SMS | Immediate |
| PH-14 | Loan Disbursement | Initiated / Disbursed / Failed | SMS, WA | Immediate |
| PH-15 | Loan EMI | T-7, T-3, T-day, +1, +7, +15, +30 | SMS, WA, Email | Per schedule |
| PH-16 | Loan Closure | Pre-close quote / Foreclosed / Paid | Email, WA | Per event |
| PH-17 | Re-engagement | 30d / 90d / 6m / 1y silent | Email, WA | Decay drip |
| PH-18 | Referral Program | Earned / Credited / Expiring | WA, Email | Per event |

## 14.2  B. Investor Lifecycle (16 triggers, highest message volume)

| ID | Trigger | Statuses | Channels | Cadence |
| --- | --- | --- | --- | --- |
| INV-01 | Lead Captured | New / Webinar reg / Webinar attended / Brochure DL | Email, WA | T+0,1,3,7,14 drip |
| INV-02 | Registration | Started / Verified / KYC Pending / Active | Email, SMS, WA | Standard |
| INV-03 | KYC + Risk Profile | CKYC / FATCA / Risk profile / Bank verified | Email, WA | Standard |
| INV-04 | Investment Opportunity Push | New match / Weekly curated / Premium yield | Email, WA, RCS | Weekly digest + alerts |
| INV-05 | Investment Soft-Commit | Interest / Doc review / Clarifications | Email, WA | Immediate |
| INV-06 | Funds Collection | Pay link / Received / Failed | SMS, Email, WA | Pending: 24h, 48h |
| INV-07 | Investment Confirmed | Assignment in progress / Confirmed / Cert issued | Email, WA | Immediate |
| INV-08 | Premium Due (10–25 yr stream) | T-30, T-15, T-7, T-3, T-day, +1, +7, +15 | All | HIGHEST VOLUME trigger |
| INV-09 | Premium Payment Confirmation | Paid to insurer / Receipt available | Email, WA | Immediate |
| INV-10 | Premium Default → Lapse Risk | Grace started / Lapse warning / Lapsed | All + call | Aggressive escalation |
| INV-11 | Maturity Approaching | T-12mo, T-6mo, T-3mo, T-1mo, T-7d | Email, WA | Per schedule |
| INV-12 | Maturity Received | Insurer paid TPE / Settled to investor | SMS, Email, WA | Immediate |
| INV-13 | Portfolio Statement | Monthly / Quarterly / Annual | Email | Cadence |
| INV-14 | Tax Documents | TDS Q1-Q4 / 80C-D / Annual | Email | Statutory |
| INV-15 | Re-investment Opportunity | Maturity-to-reinvest / New high-yield | Email, WA, RCS | Triggered |
| INV-16 | Account Notices | Monthly / T&C changes | Email | Monthly |

## 14.3  C. Insurance Partner — B2B (6 triggers)

| ID | Trigger | Statuses | Channels | Cadence |
| --- | --- | --- | --- | --- |
| INS-01 | Assignment Intimation | Submitted / Acknowledged / Approved / Rejected | Email + Portal | Per case |
| INS-02 | Premium Remittance + Allocation MIS | Paid / MIS attached / Confirmed / Discrepancy | Email + Excel | Monthly batch — reuses existing MIS Pipeline |
| INS-03 | MIS Reconciliation | Sent / Confirmed / Variance | Email + Excel | Monthly |
| INS-04 | Query Resolution | Raised / Response / Closed | Email | Per case |
| INS-05 | Maturity / Claim Coordination | Initiated / Docs / Approved / Settled | Email | Per case |
| INS-06 | Regulatory / KYC Refresh | IRDAI shared / KYC refresh | Email | Per cadence |

## 14.4  D. Internal Ops / Sales / Agents (6 triggers)

| ID | Trigger | When fires | Channels | Cadence |
| --- | --- | --- | --- | --- |
| OPS-01 | New Lead Allocated | Lead created → assigned | Slack/Teams + Email | Real-time |
| OPS-02 | Daily Standup Briefing | Pipeline + stuck + KPIs | Slack + Email | Daily 9am IST |
| OPS-03 | High-Value Escalation | Deal ≥ ₹50L stuck / VIP query | Slack + SMS | Real-time |
| OPS-04 | Premium Default Alert | Investor non-pay → lapse risk | Slack + Email | Real-time |
| OPS-05 | KYC Stuck | >7 days in KYC | Slack | Daily digest |
| OPS-06 | Compliance Deadline | IRDAI / GST / TDS | Email + Calendar | Pre-deadline |

## 14.5  E. Regulatory / Statutory (3 triggers)

| ID | Trigger | Cadence |
| --- | --- | --- |
| REG-01 | IRDAI Filing — quarterly + annual | Per regulator schedule |
| REG-02 | TDS certificates to investors | Quarterly |
| REG-03 | GST invoices | Per transaction |

# 15. Channel Strategy

Channel selection is derived from audience, message intent and compliance class — never from preference.

| Channel | Best for | Avoid for | Indian compliance gate |
| --- | --- | --- | --- |
| Email | Long-form, attachments (statements, certificates), legal copy | Time-critical alerts (open-rate too low) | DPDPA consent, IT Act 2000 |
| SMS | OTP, transactional confirmations, due-day urgent reminders | Promotional content to opted-out users; long messages | DLT registration (PE, Header, Template, Entity ID); TRAI |
| WhatsApp | Conversational service messages, multilingual, rich media | Bulk promotional without opt-in; promotional outside template categories | Meta BSP template approval; correct category (Marketing / Utility / Authentication); 24h session window |
| RCS | Carrier-rich interactions: pay-now buttons, carousels for opportunity push | Audiences whose handsets / carriers do not yet support RCS | Same DLT regime as SMS in India |
| Slack/Teams | Internal alerts, allocations, escalations | Anything customer-facing | Internal information classification only |
| Voice/IVR | Premium-default last-mile call (Phase 5+) | First-touch unknown audience | TRAI commercial-comms regulations + DND |

PART V

Solution

# 16. Template Management — Architectural Pillar

Templates are first-class entities, decoupled from triggers. A trigger references one or more templates by ID; the same template can be reused across triggers (e.g. a single OTP template serves Registration, Login and e-Sign). This decoupling is the single most important architectural decision in the system: it prevents content drift, enables version control, makes localisation tractable and produces an audit trail.

## 16.1  Template Lifecycle

Every template moves through a defined state machine. State transitions are recorded with actor, timestamp and rationale.

| DRAFT | ▶ | REVIEW | ▶ | APPROVED | ▶ | ACTIVE | ▶ | DEPRECATED | ▶ | ARCHIVED |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| State | Meaning | Who can transition | Permitted next states |
| --- | --- | --- | --- |
| draft | Author is composing; not yet reviewable | Author | review, archived |
| review | Awaiting compliance and brand-voice review | Author submits | approved, draft (returned) |
| approved | Compliance + brand approved; ready to activate | Compliance + Brand Lead | active, draft (revoked) |
| active | In use by one or more triggers; lint passes | Operator / scheduler | deprecated |
| deprecated | Superseded by a newer version; remains for audit only | Operator | archived |
| archived | Frozen, read-only, retained for audit | System | (terminal) |

## 16.2  Versioning Rules (semver)

| Bump | When | Example |
| --- | --- | --- |
| MAJOR (x.0.0) | Breaking change: variable added/removed/renamed; intent changes; channel changes | 1.4.2 → 2.0.0 when adding {{xirr}} variable |
| MINOR (1.x.0) | Material wording change; new disclaimer; tone shift | 1.4.2 → 1.5.0 when softening urgency wording |
| PATCH (1.4.x) | Typo, punctuation, formatting; no semantic change | 1.4.2 → 1.4.3 when fixing apostrophe |

## 16.3  Template Schema (YAML)

Templates are stored as YAML files in the repository under templates/<audience>/<channel>/<id>.yaml. Schema (illustrative):

template_id: TPL-PH-KYC-PENDING-WA-001 name: "KYC Pending Reminder — WhatsApp" version: 1.2.0 status: active # draft¦review¦approved¦active¦deprecated¦archived audience: policyholder # policyholder¦investor¦insurer¦internal¦regulator language: en # en¦hi¦ta¦te¦mr¦bn¦kn¦gu¦ml¦pa channel: whatsapp # email¦sms¦whatsapp¦rcs¦slack category: utility # marketing¦utility¦authentication (WA BSP) compliance_class: service # transactional¦service¦promotional sender_identity: TPE_CARE # references senders.yaml brand_voice: empathetic # references voices.yaml intent: "Nudge PH to complete KYC; respect cadence; do not pressure" variables: - name: ph_name required: true fallback: "Customer" - name: kyc_link required: true type: short_url disclaimers: [irdai_solicitation_short] # references disclaimers.yaml footer: [opt_out_short] # references footers.yaml content: body: ¦ Hello {{ph_name}}, Your KYC is still pending. Complete it in 2 minutes here: {{kyc_link}} Reply STOP to opt out. Need help? Reply HELP. parent_template: null # for variants/translations variants: - TPL-PH-KYC-PENDING-WA-001-hi # Hindi variant used_by_triggers: [PH-03] metadata: created_by: ashish.satyam created_at: 2026-04-26 approved_by: compliance.lead approved_at: 2026-04-26 brand_review_by: cx.head reuse_count: 1

## 16.4  Template Management Capabilities

| Capability | Description | Surface |
| --- | --- | --- |
| Authoring | Create / edit templates with schema validation, variable hints, character-limit warnings (SMS 160, WA 1024) | /tpe-template new, /tpe-template edit |
| Versioning | Semver bumps with diff against prior; rationale captured | /tpe-template version <id> |
| Approval workflow | Submit for review; reviewer approves/rejects with notes | /tpe-template review <id> |
| Variant linking | Mark a template as language or A/B variant of another; sync schema | /tpe-template variant <parent> <child> |
| Channel rendering | Single intent → channel-specific render with limits enforced | /tpe-template render <id> |
| Compliance lint | Run all relevant lint rules on demand or pre-approval | /tpe-comply check <id> |
| Search / discover | Filter by audience, channel, category, status, used-by-trigger | /tpe-template search |
| Reuse tracking | Show all triggers that reference a template before deprecation | /tpe-template usage <id> |
| Catalogue export | Generate human-readable PDF/HTML index of all approved templates | /tpe-library export |
| Bulk import | Migrate spreadsheet content into template files (one-time + ongoing sync) | /tpe-library import <xlsx> |
| Diff | Show change between any two versions of a template | /tpe-template diff <id> v1 v2 |
| Localisation queue | Surface templates whose EN parent has changed but variants have not | /tpe-l10n queue |
| Deprecation safety | Block deprecation if template is still referenced by an active trigger | Pre-condition check |
| Audit trail export | Per-template chronological log: state transitions, edits, approvals, sends | /tpe-template audit <id> |

## 16.5  Reuse Examples

| Template family | Used by triggers | Without reuse |
| --- | --- | --- |
| TPL-OTP-SMS-001 | PH-02 Registration, PH-08 e-Sign, INV-02 Registration, Login | 4 near-identical drafts, 4 risks of drift |
| TPL-IRDAI-DISCLAIMER-LONG | Every PH and INV email/RCS promotional template | Each template re-types the disclaimer; one regulator update = N edits |
| TPL-OPT-OUT-FOOTER-WA | All WhatsApp promotional templates | Inconsistent opt-out wording → DPDPA risk |
| TPL-PH-KYC-PENDING-WA-001 | PH-03 KYC at week-1, week-2, week-3, week-4 (with date variable) | 4 duplicated templates instead of 1 + cadence rule |

# 17. Solution Architecture

Three pillars, file-system-resident, Git-versioned, human-readable. No database, no server, no hosting in v1. Read-only consumption by future channel integrators.

| PILLAR 1 Trigger Catalogue WHEN to communicate. Lives at: triggers/<audience>/<id>.yaml Owner: Customer Experience 49 lifecycle events with statuses, cadence and template references. | PILLAR 2 Template Library WHAT to say. Lives at: templates/<audience>/<channel>/ Owner: Brand + Compliance Reusable, versioned content atoms with full lifecycle (draft → archived). | PILLAR 3 Channel Renderer HOW to ship it. Lives at: skills/render/* Owner: Engineering Transforms template + variables → channel-specific payload (Email, SMS, WA, RCS). |
| --- | --- | --- |

### Data flow

TRIGGER (PH-03 KYC, status=pending, attempt=2) │ ├── reads cadence rule → "weekly × 4, then monthly × 4, then close" ├── selects template_id by status, channel, language, audience │ ▼ TEMPLATE (TPL-PH-KYC-PENDING-WA-001 v1.2.0, status=active) │ ├── compliance lint: DLT ✓ IRDAI ✓ WA category=utility ✓ opt-out ✓ ├── variable bind: {{ph_name}}, {{kyc_link}} → values │ ▼ CHANNEL RENDERER (whatsapp) │ ├── enforces 1024-char limit, BSP-template syntax, button schema │ ▼ DISPATCH PAYLOAD (JSON; ready for MSG91 / Karix / Gupshup)

## 17.1  Repository layout

tpe-communication-system/ ├── docs/ │ ├── TPE_Communication_System_SOW.docx (this document) │ ├── runbook.md │ ├── template-author-guide.md │ └── compliance-reference.md ├── triggers/ │ ├── policyholder/ (18 yaml files) │ ├── investor/ (16 yaml files) │ ├── insurer/ ( 6 yaml files) │ ├── internal/ ( 6 yaml files) │ └── regulatory/ ( 3 yaml files) ├── templates/ │ ├── policyholder/{email,sms,whatsapp,rcs}/ │ ├── investor/{email,sms,whatsapp,rcs}/ │ ├── insurer/email/ │ ├── internal/{slack,email}/ │ └── regulatory/email/ ├── library/ │ ├── senders.yaml (sender identities + DLT IDs) │ ├── voices.yaml (brand-voice rules per audience) │ ├── disclaimers.yaml (IRDAI mandatory text variants) │ ├── footers.yaml (opt-out, address, grievance) │ ├── variables.yaml (canonical token catalogue) │ ├── languages.yaml (locales + glyph rules) │ └── compliance-rules.yaml (lint rule definitions) ├── skills/ (Claude Code skill .md files) │ ├── tpe-template/ │ ├── tpe-trigger/ │ ├── tpe-comply/ │ ├── tpe-render/ │ └── tpe-library/ └── tests/ ├── lint/ (compliance lint test pack) ├── render/ (channel render goldens) └── triggers/ (trigger-template wiring tests)

# 18. Skill Catalogue (Claude Code surface)

The system is operated through twenty-two slash commands invoked from Claude Code. Commands cluster around three intents — author templates and triggers, validate compliance, and render or (eventually) dispatch. The phase column shows when each command becomes available; nothing in P5 is required for the library or lint to deliver value.

| Slash command | Purpose | Phase |
| --- | --- | --- |
| /tpe-template new | Create a new template from schema with prompts for required fields | P1 |
| /tpe-template edit | Edit existing template with version-bump prompt | P1 |
| /tpe-template version | Bump version (major/minor/patch) with rationale capture | P1 |
| /tpe-template review | Submit for review or approve/reject with notes | P1 |
| /tpe-template variant | Link a variant template to its parent (translation or A/B) | P3 |
| /tpe-template render | Render template + sample variables into channel-specific output | P1 |
| /tpe-template diff | Show diff between any two versions | P1 |
| /tpe-template usage | List all triggers referencing a template | P1 |
| /tpe-template audit | Chronological log: state transitions, edits, approvals | P2 |
| /tpe-trigger new | Create a new trigger entry: statuses, cadence, template references | P1 |
| /tpe-trigger edit | Edit cadence or template references on a trigger | P1 |
| /tpe-trigger preview | Simulate trigger across all statuses → render every message it produces | P2 |
| /tpe-comply check | Run all relevant compliance lint rules on a template or trigger | P4 |
| /tpe-comply rules | List active compliance rules and which categories they apply to | P4 |
| /tpe-render <channel> | Render any template into the specified channel (with sample data) | P1 |
| /tpe-library search | Filter library by audience, channel, status, used-by, language | P1 |
| /tpe-library export | Export approved library as DOCX or HTML index for stakeholder review | P2 |
| /tpe-library import | One-time migration of existing spreadsheet content into templates | P2 |
| /tpe-l10n queue | Show templates whose EN parent has changed but variants have not | P3 |
| /tpe-l10n translate | Author a language variant from a parent template | P3 |
| /tpe-send dryrun | [Phase 5] Build dispatch payload without sending | P5 |
| /tpe-send dispatch | [Phase 5] Send via configured channel provider | P5 |

PART VI

Compliance, Security & Quality

# 19. Compliance & Regulatory Layer

Compliance is the most consequential and the most easily neglected part of regulated communication. Six regimes apply simultaneously to a typical TPE message — DLT for SMS, IRDAI for insurance disclosures, WhatsApp BSP for template categorisation, DPDPA for consent and opt-out, FATCA / KYC for investor flows, and Income-Tax (TDS) for statutory documents. The lint engine encodes them as machine-checkable rules so a missed disclaimer is caught at the approval gate, not by the regulator.

Every approved template is validated against the active compliance ruleset before it can transition to ‘active’. Rules are externalised as YAML so a regulator update does not require code changes.

| Regime | Rule examples | Surface in lint |
| --- | --- | --- |
| TRAI / DLT (SMS) | Header registered; Template ID present; Entity (PE) ID present; transactional vs promotional category matches sender; promotional time-window check | /tpe-comply check → DLT_* |
| IRDAI | ‘Insurance is the subject matter of solicitation’ disclaimer present in promo; returns disclaimer; grievance redressal contact; IRDAI registration number on annual statements | /tpe-comply check → IRDAI_* |
| WhatsApp BSP (Meta) | Template category matches content (Marketing/Utility/Authentication); variable count and order matches approved Meta template; media size limits; 24h session window respected for free-text | /tpe-comply check → WA_* |
| DPDPA (India Data Protection) | Opt-out instruction present in promotional channels; consent reference for marketing categories; PII masking in audit logs | /tpe-comply check → DPDPA_* |
| FATCA / KYC | Investor onboarding templates reference FATCA self-declaration; CKYC where applicable; risk-profile reference on investment opportunity push | /tpe-comply check → KYC_* |
| Income Tax (TDS) | Section / rate references in TDS certificate templates; PAN-format validation in variables; FY references machine-derived not hard-coded | /tpe-comply check → TDS_* |
| Internal brand-voice | PH-facing templates avoid urgency-marketing terms in stop-list; investor-facing templates do not promise specific returns; tone matches audience profile | /tpe-comply check → BRAND_* |

Lint pass before approval, not after dispatch. Compliance failure detected after a message has been sent is, in practice, irreversible — the regulator’s clock has started. The lint engine therefore runs as a mandatory pre-condition for the review → approved transition. An override path exists for urgent cases; overrides are logged and reviewed at the next phase gate.

# 20. Security & Privacy Framework

Communication systems concentrate Personally Identifiable Information (PII): names, phone numbers, policy numbers, premium amounts, bank-last-four. Misuse, leak or unauthorised access creates regulatory exposure under DPDPA and reputational damage with both sides of the marketplace. The controls below are designed-in, not bolted-on, and are validated as part of acceptance (Section 24).

## 20.1  Data classification

| Class | Examples in this system | Handling rule |
| --- | --- | --- |
| PII — High | ph_name, ph_phone, ph_email, inv_name, PAN, bank_last4 | Tokenise in templates; never log raw; mask in audit; HTTPS only in transit |
| PII — Medium | policy_no, premium_amount, due_date, surrender_value | Encrypted at rest; access on least-privilege; redact in screenshots |
| Operational | trigger_id, template_id, status, cadence | Public within company; safe to log |
| Brand confidential | Disclaimer text, brand voice rules | Internal-only; not for external comms |

## 20.2  Controls

| Control area | Control |
| --- | --- |
| Access control | Role-based: author / reviewer / operator / admin; least-privilege; reviewed quarterly |
| Authentication | SSO via TPE identity provider; MFA mandatory for reviewer/admin |
| Authorisation gates | review → approved transition requires Compliance + Brand reviewer; no self-approval |
| Encryption — transit | TLS 1.2+ for all network calls; certificate-pinned for BSP/SMS gateway |
| Encryption — rest | AES-256 for repository storage; key rotation per TPE security policy |
| Secret management | Channel-provider API keys in vault; never in repo; rotated per provider policy |
| Audit log | Append-only; per-template state transitions, edits, sends; PII masked |
| PII minimisation | Variables resolved at render time, not stored in audit log |
| Backup & recovery | Daily Git-replicated; weekly snapshot; documented RPO 24h / RTO 4h |
| Vulnerability mgmt | Quarterly dependency scan; security review at every major version |

## 20.3  DPDPA alignment

| DPDPA principle | How this system aligns |
| --- | --- |
| Lawful processing | Templates carry compliance_class; lint blocks promotional sends without consent reference |
| Purpose limitation | Trigger taxonomy makes intent explicit; templates linked to triggers; reuse is auditable |
| Data minimisation | Variables declare what is needed; lint flags unused PII variables |
| Storage limitation | Audit retains state transitions, not raw PII; backups retained per data-retention policy |
| Accuracy | Variables source from system of record; fallbacks prevent broken renders |
| Notice & consent | Opt-out wiring on every promotional template; opt-out evidence stored at BSP |
| Rights of data principals | Subject-access response supported via audit-trail export; deletion on request |
| Breach notification | Incident runbook (Section 37) covers detection, escalation, regulator notification |

# 21. Quality Assurance & Testing Strategy

Quality is engineered, not reviewed in. The system is tested at five levels — schema, lint, render, trigger-template wiring and end-to-end — each catching a different class of defect. Test packs are part of the deliverable (Section 23) and run on every change.

## 21.1  Test levels

| Level | What it catches | Example | Run when |
| --- | --- | --- | --- |
| L1 Schema | Malformed YAML, missing required fields, invalid enum values | Template with no compliance_class fails parse | Pre-commit + CI on every push |
| L2 Lint | Compliance violations: DLT, IRDAI, WA BSP, DPDPA, brand-voice | WhatsApp template marked Marketing without opt-out | Pre-commit + before review → approved transition |
| L3 Render | Channel-renderer regressions: char limits, button schema, encoding | SMS body exceeds 160 chars after variable substitution | CI on every push |
| L4 Wiring | Trigger references a template that does not exist or is deprecated | PH-03 cadence references a template that was archived | CI nightly + before phase-gate |
| L5 End-to-end | Full flow: trigger fires → template selected → lint passes → renders to channel-valid payload | PH-03 KYC pending week-2 → WA template → MSG91 dry-run payload | Phase-gate + before any production release |

## 21.2  Acceptance test pack (per phase)

| Phase | Pack composition |
| --- | --- |
| P1 | ≥ 30 schema tests + 5 lint rules + 2 render goldens + PH-03 E2E |
| P2 | + 1 wiring test per PH trigger; render goldens for Email + WA × all PH active statuses |
| P3 | + INV/INS/OPS/REG wiring; Hindi-language render goldens; localisation queue test |
| P4 | + ≥ 30 lint rules across 6 regimes; approval-gate enforcement test; audit-trail export test |
| P5 | + MSG91/Karix/Gupshup dry-run goldens; WA BSP template ID validation; receipt ingest |

## 21.3  Defect severity & SLA

| Severity | Definition | Response SLA | Resolution SLA |
| --- | --- | --- | --- |
| ● Sev-1 (H) | Compliance violation in active template OR data leak | 1h | Same business day; rollback if needed |
| ● Sev-2 (H) | Active template broken (cannot render) OR active trigger silent | 4h | 1 business day |
| ● Sev-3 (M) | Active template flawed but still rendering (typo, mild wording) | 1 business day | 1 sprint |
| ● Sev-4 (L) | Cosmetic / docs / non-active template | 1 sprint | Backlog |

PART VII

Delivery

# 22. Implementation Phases & Timeline

Five phases. Each phase produces an independently consumable artefact, so a stop after any phase still leaves usable value behind. Phase 5 (live dispatch via channel providers) is the only phase that depends on external commercial relationships — DLT, BSP and SMS-gateway contracts — and is therefore held as optional and separately gated.

| P1 Foundation 5 days | ▶ | P2 PH Library 8 days | ▶ | P3 INV+INS+OPS+REG+HI 7 days | ▶ | P4 Compliance Layer 5 days | ▶ | P5 Live Dispatch (opt) 10 days |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Phase | Name | Days | Outcome |
| --- | --- | --- | --- |
| P1 | Foundation | 5 | Repo scaffolded; YAML schemas finalised; first 5 skills working end-to-end on a single trigger (PH-03 KYC) and 1 template; renderer for Email + WhatsApp. |
| P2 | Content Library v1 — Policyholder | 8 | All 18 PH triggers authored, EN only, all statuses; ~50 templates in library; export as DOCX index for stakeholder review. |
| P3 | Investor + Insurer + Internal + Hindi | 7 | 16 INV + 6 INS + 6 OPS + 3 REG triggers added; Hindi variants for all PH-facing templates; localisation queue working. |
| P4 | Compliance Layer | 5 | Full lint engine; DLT, IRDAI, WhatsApp BSP, DPDPA, brand-voice rules; approval gate enforced; audit-trail export. |
| P5 | Live Dispatch (optional, gated) | 10 | MSG91 / Karix / Gupshup MCP integration; WhatsApp BSP API; dry-run + dispatch slash commands; delivery-receipt ingest. |

Total core delivery (P1–P4): 25 working consultant-days. P5 is gated on channel-provider selection, contract, sandbox credentials and budget. P5 is not on the critical path for value realisation — the library and lint provide value immediately even with manual dispatch.

# 23. Deliverables

The artefacts below constitute the complete deliverable set for the engagement. Each is a tangible output that the Client receives at, or by the end of, the named phase. Acceptance procedure is in Section 24.

| Phase | Artefact | Format |
| --- | --- | --- |
| P1 | Repository scaffold + YAML schemas | Git repo |
| P1 | 5 core slash commands operational | Skill .md files |
| P1 | Renderer (Email, WhatsApp) reference implementation | Code |
| P1 | Walk-through of PH-03 KYC end-to-end | Recorded session |
| P2 | All 18 PH triggers authored | YAML files |
| P2 | ~50 EN templates in library | YAML files |
| P2 | Stakeholder review pack (DOCX export of library) | DOCX |
| P2 | Bulk import from current spreadsheet (one-time) | Migration script + report |
| P3 | 31 additional triggers (INV + INS + OPS + REG) | YAML files |
| P3 | Hindi variants for all PH-facing templates | YAML files |
| P3 | Localisation queue dashboard (markdown report) | Markdown |
| P4 | Compliance lint engine + 30+ rules | Code + YAML rules |
| P4 | Approval gate enforced on lifecycle transition | Skill behaviour |
| P4 | Audit-trail export per template | Markdown / JSON |
| P4 | Compliance reference card (printable) | PDF |
| P5 | MSG91 / Karix / Gupshup integration (gated) | MCP integration |
| P5 | WhatsApp BSP integration (gated) | MCP integration |
| P5 | Dispatch dry-run + send commands | Skill .md files |
| All | Test packs (lint, render, trigger-template wiring) | Code |
| All | Runbook + author guide + compliance reference | Markdown / DOCX |

# 24. Acceptance Criteria & Procedure

Acceptance is the mechanism by which a deliverable transitions from “submitted” to “accepted”, releasing the corresponding milestone payment (Part XI) and closing the phase. The criteria below define what each phase must demonstrate; the procedure below defines how acceptance is recorded, how rejection works, and what happens if the Client does not respond.

## 24.1  Acceptance criteria (per phase)

| Phase | Acceptance criteria |
| --- | --- |
| P1 | Repo passes schema-validation tests; 5 slash commands operate without error on PH-03 KYC; Email + WhatsApp render produces output that matches a stakeholder-approved sample byte-for-byte (excluding timestamps and machine IDs). |
| P2 | All 18 PH triggers have at least one approved template per active status; stakeholder review pack received written approval from CX Head; spreadsheet import covers 100% of current PH content with diff report attached. |
| P3 | Investor, Insurer, Internal, Regulatory triggers fully authored; Hindi variants exist for all PH-facing templates and pass language-specific lint; localisation queue reports zero unsynced templates. |
| P4 | Lint engine has at least 30 rules across the six regimes; review → approved transition is blocked on lint failure; audit-trail export is reviewable and reconciles with Git history. |
| P5 (if executed) | Dry-run produces provider-valid payload for MSG91 / Karix / Gupshup; dispatch successfully sends and ingests delivery receipts in sandbox; production cutover requires separate go-live sign-off. |

## 24.2  Acceptance procedure

On phase completion, the Consultant submits an Acceptance Notice to the Client containing: (a) a phase-summary statement that each criterion in 24.1 has been met; (b) evidence (test logs, recorded walk-through link, deliverable artefacts in the repository); and (c) an acceptance form for counter-signature. Acceptance proceeds as below.

| State | Trigger | SLA | Effect |
| --- | --- | --- | --- |
| Submitted | Consultant emails Acceptance Notice + evidence to Client Engagement Owner | Day 0 | Acceptance window opens |
| Under review | Client reviews against 24.1 criteria | 5 business days | Client may request walk-through; SLA may be extended by mutual written agreement, max +5 days |
| Accepted (express) | Client signs Acceptance Form | Within window | Triggers milestone invoice (Part XI). Phase closed. |
| Rejected | Client issues Rejection Notice citing specific 24.1 criteria not met | Within window | Rework triggered (24.3) |
| Accepted (deemed) | Client neither accepts nor rejects within the window | End of window | Deliverable deemed accepted; milestone invoice triggered. |

## 24.3  Rejection notice and rework

- A Rejection Notice must be in writing and must reference the specific clause(s) of 24.1 alleged to be unmet. Generic dissatisfaction or change-of-mind requests do not constitute rejection — they are change requests under Section 27.

- On valid rejection, the Consultant has 5 business days (or such longer period agreed in writing) to remediate and resubmit. The acceptance window then restarts on the resubmission date.

- Rework cap. The Consultant’s rework obligation per phase is capped at 25% of the phase’s consultant-days. Rework beyond that cap is treated as a change order under Section 41 and charged at the rate card.

- Where rejection is later determined to have been raised in bad faith or without specific reference to 24.1, the original Acceptance Notice date is restored.

## 24.4  Materiality and partial acceptance

Where a deliverable substantially meets the criteria but a non-material defect is identified, the Parties may agree in writing to a Conditional Acceptance: the milestone payment is released and the defect is logged as a Sev-3 item (Section 21.3) for remediation within the next phase. Conditional Acceptance does not extend the project timeline or increase the contract value.

Why deemed acceptance matters. Without a closing window, “acceptance” is whatever the Client says it is, indefinitely, and milestone payments stall while the project moves on. The 5-business-day window is a standard market practice for SOWs of this size; it is enough time for thorough review by Client approvers and tight enough to keep the engagement on cadence.

PART VIII

Governance

# 25. Roles & Responsibilities (RACI)

R = Responsible, A = Accountable, C = Consulted, I = Informed.

| Activity | Consult. | Eng (TPE) | CX | Comply | CTO | Sponsor |
| --- | --- | --- | --- | --- | --- | --- |
| Schema design + scaffolding | R/A | C | I | I | C | I |
| Template authoring | R | C | A | C | I | I |
| Compliance rule definition | R | C | C | R/A | I | I |
| Compliance review of templates | C | C | C | R/A | I | I |
| Brand-voice review | C | I | R/A | C | I | I |
| Channel renderer code | R/A | C | I | I | C | I |
| Spreadsheet import (one-time) | R | C | A | C | I | I |
| Phase sign-off | R | I | C | C | C | A |
| Phase 5 channel-provider selection | C | C | C | C | R/A | I |
| Audit-evidence production | R | C | C | A | I | I |
| Acceptance Notice issuance | R/A | C | I | I | I | I |
| Acceptance counter-signature | C | C | C | C | C | R/A |

# 26. Communication Management Plan

How the engagement itself communicates — distinct from the communication-system being built. Defined cadence, owners and channels prevent the project from generating its own coordination drag.

| Forum | Frequency | Owner | Audience | Format | Output |
| --- | --- | --- | --- | --- | --- |
| Daily standup | Daily 10:30 IST | Consultant | TPE Eng | Slack thread | Daily update + blockers |
| Weekly status | Friday 16:00 IST | Consultant | All approvers | DOCX 1-pager + Slack | Status, risks, decisions |
| Phase-gate review | End of P1, P2, P3, P4 | Consultant | All approvers | Live demo + DOCX | Sign-off → next phase |
| Compliance review queue | Continuous | Compliance | Authors | /tpe-template review | Approval / rejection |
| Brand review queue | Continuous | Brand Lead | Authors | /tpe-template review | Approval / rejection |
| Risk review | Bi-weekly | Consultant | CTO + Sponsor | Updated Risk Register | New / closed risks |
| Stakeholder digest | Monthly | Consultant | All stakeholders | Email | Progress + asks |
| Post-mortem | Per Sev-1/Sev-2 | Consultant | All approvers | Markdown | Action items |

Information radiator, not push. Status is published to a single source (the Slack channel + weekly DOCX). Approvers pull when they need to; the Consultant does not chase or duplicate. Push is reserved for blockers and phase-gate decisions.

# 27. Change Management Process

Any change to scope, effort, timeline, deliverables, commercial terms or legal terms follows the process below. Change requests captured informally — in Slack, email or hallway — must be re-stated as a formal Change Request before they take effect.

## 27.1  Change request lifecycle

| RAISED | ▶ | TRIAGED | ▶ | ASSESSED | ▶ | DECIDED | ▶ | APPLIED | ▶ | CLOSED |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| State | Owner | SLA | Output |
| --- | --- | --- | --- |
| raised | Anyone | — | CR ticket with title + rationale |
| triaged | Consultant | 1 business day | Severity + initial impact estimate |
| assessed | Consultant + reviewers | 3 business days | Effort delta, scope delta, risk delta, cost delta |
| decided | CCB | Next CCB or 5 days | Approve / reject / defer |
| applied | Consultant | Per agreed plan | Document updated; new version cut |
| closed | Consultant | Within 1 sprint | CR archived with audit |

## 27.2  Change Control Board (CCB)

| Members | Sponsor, CTO, Compliance, CX, Consultant |
| --- | --- |
| Quorum | Sponsor + CTO + (one of Compliance / CX) + Consultant |
| Frequency | On demand for Sev-1 / Sev-2; otherwise weekly when CRs are open |
| Decision rule | Consensus; deadlock escalates to Sponsor |
| Authority | Approve / reject / defer scope, effort, deliverable, commercial changes |
| Records | CCB minutes filed against the CR; Version History updated on apply |

## 27.3  Change classification

| Class | Triggers | Decision authority | Commercial effect |
| --- | --- | --- | --- |
| Minor | Editorial, prose, tone, examples; no effort impact | Consultant | None |
| Moderate | ≤ 1 day effort; no scope change; no deliverable change | Consultant + 1 approver | Absorbed within phase budget |
| Material | > 1 day effort OR scope/deliverable change OR risk change | Full CCB | Change order issued at rate card (Section 41) |
| Critical | Compliance violation surfaced OR Sponsor-level commercial | Full CCB + Sponsor | Change order + commercial impact assessment |

# 28. Service Level Agreements

SLAs the delivered system commits to (post go-live), and SLAs the Consultant commits to during build. The first set governs operations; the second set governs delivery. Breach handling is in 28.3.

## 28.1  Operational SLAs (post go-live)

| Service | Metric | Target | Measurement |
| --- | --- | --- | --- |
| Template approval queue | Time from review → approved | ≤ 24h business day | Per template, audit log |
| Lint engine availability | Uptime | 99.5% rolling 30 days | Pre-commit + CI metrics |
| Render correctness | Sev-1 incidents per quarter | 0 | Production observation |
| OTP delivery (P5) | P95 delivery latency | ≤ 10s | MSG91 / BSP receipts |
| Premium-due send (P5) | Send-window adherence | 100% within DLT 9–21 IST window | DLT compliance report |
| Audit-trail export | Time to produce per-template audit | ≤ 60s | Operational test |
| Subject-access response | DPDPA SAR turnaround | ≤ 7 calendar days | Incident log |

## 28.2  Delivery SLAs (during build)

| Activity | Target SLA | Owner |
| --- | --- | --- |
| Phase-gate review pack ready | T-2 business days before review | Consultant |
| Compliance review of template | ≤ 24h business day | Compliance Lead (Client) |
| Brand review of template | ≤ 24h business day | Brand Lead (Client) |
| Reviewer-blocked CR triage | Same business day | Consultant |
| Sev-1 defect response | 1h | Consultant |
| Weekly status report publication | Friday 16:00 IST | Consultant |
| CR decision (Material+) | Within 5 business days of raised | CCB |
| Acceptance Notice review | 5 business days (per Section 24.2) | Client |

## 28.3  SLA breach handling

- First breach in a rolling 30-day window: documented in weekly status, root-cause noted, no further action.

- Second breach in 30 days: Consultant escalates to CTO + Sponsor; mitigation plan due within 3 business days.

- Three or more breaches in 30 days: CCB session called; phase plan re-baselined if material.

- Breaches by the Client (e.g. delayed reviewer turnaround) extend the corresponding phase SLA on a day-for-day basis and form the basis for any milestone-payment timing dispute.

- Breaches are visible — no breach is concealed by re-defining the metric.

# 29. Governance & Review Cadence

Governance forums distribute authority and feedback through the engagement lifecycle. Decisions made outside these forums are non-binding until ratified at the next applicable forum.

| Forum | Frequency | Attendees | Purpose |
| --- | --- | --- | --- |
| Engineering standup | Daily | Consultant + TPE Eng | Build coordination |
| Weekly status | Weekly | Consultant + CX Head + CTO | Progress, risks, decisions needed |
| Phase-gate review | End of each phase | Consultant + CX + Compliance + CTO + Sponsor | Acceptance and go/no-go for next phase |
| Compliance approval queue | Continuous | Compliance Reviewer | Template-level approvals |
| Brand-voice approval queue | Continuous | Brand Lead | Tone and copy approvals |
| Quarterly post-go-live | Quarterly | All stakeholders | Measure objectives O1–O7 against baselines |
| Annual SOW review | Annually post go-live | Sponsor + Consultant | Renewal, scope expansion or sunset |

PART IX

Risk & Dependencies

# 30. Assumptions

This SOW is priced and scoped against the assumptions listed below. If any assumption is invalidated during the engagement, it is treated as a Material change request under Section 27 and may carry effort, timeline or commercial impact.

| # | Assumption | Validation |
| --- | --- | --- |
| A1 | Existing customer-data store is queryable with stable schemas (PH, Investor, Policy, Premium). | Client to confirm schema before P2 |
| A2 | DLT registration (PE ID, Header, Template IDs) exists or will exist by start of P5. | Client owns; gates P5 |
| A3 | WhatsApp BSP partner contracted by start of P5. | Client owns; gates P5 |
| A4 | Compliance Lead and CX Head available for ~4 hours/week during build. | Standing weekly slot |
| A5 | No new audience added in v1; v2 will be a separate SOW. | Locked at signing |
| A6 | Only EN and HI languages in v1; regional languages are v2. | Locked at signing |
| A7 | Existing MIS Pipeline continues to serve INS-02 attachments; no rebuild. | Confirmed at scoping |
| A8 | Client provides reasonable cooperation, timely access to systems, sample data, and reviewer time per Section 26. | Standard delivery assumption |
| A9 | Engagement is delivered remotely; on-site requirement, if any, is by mutual agreement and reimbursable per Section 41. | Default remote |
| A10 | Rate card and milestone amounts in Part XI are denominated in INR and exclusive of GST and statutory taxes. | Locked at signing |

# 31. Dependencies

External factors required for delivery on the agreed cadence. Late dependencies extend their corresponding phase on a day-for-day basis (Section 28.3) and may carry commercial impact under Section 41.

| # | Dependency | Phase blocked | Owner | Needed by |
| --- | --- | --- | --- | --- |
| D1 | Customer-data sample set with PII tokenised | P1 | Client Eng | Day 1 |
| D2 | DLT template IDs registered (or registration plan) | P5 | Client CTO | Start of P5 |
| D3 | WhatsApp BSP credentials and template approval pipeline | P5 | Client CTO | Start of P5 |
| D4 | Brand voice samples + style guide (existing assets) | P2 | Client CX | Start of P2 |
| D5 | Compliance reference: existing IRDAI / DPDPA disclaimers as currently used | P4 | Client Compliance | Start of P4 |
| D6 | Spreadsheet of current message templates (for import) | P2 | Client Ops | Day 1 of P2 |
| D7 | Reviewer availability (CX, Compliance, Brand) | P2–P4 | Client | Continuous |
| D8 | Counter-signed SOW + mobilisation invoice paid | All | Client Sponsor + Finance | Day 0 |

# 32. Risk Register

Risks are scored on Probability (P) and Impact (I), each H / M / L. Severity is the higher of the two, reviewed bi-weekly (Section 26). Residual risk is the level remaining after the mitigation. Closed risks remain in this register for audit and are visible at phase-gate reviews.

| ID | Risk | P | I | Sev | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Reviewer bandwidth shortfall (Compliance / CX) delays approval queue | M | H | H | Standing weekly slot; pre-approved disclaimer library in P4 to reduce per-template touch | Sponsor |
| R2 | Compliance disclaimer text changes mid-build (IRDAI update) | L | M | M | Externalise disclaimers to library/disclaimers.yaml; one-line change | Compliance |
| R3 | DLT registration delay (P5 only) | M | H | H | Treat P5 as gated; Phase 1–4 deliver value without it | CTO |
| R4 | WhatsApp template rejection by Meta | M | M | M | Pre-validate against BSP rules in P4; small-batch approval first | CTO |
| R5 | Existing spreadsheet content quality below assumption | M | M | M | Migration produces a diff report; non-conforming rows flagged for manual | Ops |
| R6 | Hindi/regional variant volume larger than anticipated | M | M | M | Localisation queue prioritises by trigger volume; v2 covers regional | CX |
| R7 | Scope creep: unrequested triggers, new audiences, dispatch features mid-build | H | M | H | Strict change-management process (Section 27); CCB authority | Sponsor + Consultant |
| R8 | Compliance violation in active template post go-live | L | H | M | Lint engine at approval gate; audit trail; runbook for hot-fix | Compliance + Consultant |
| R9 | Investor premium-default rate does not improve at 6 months | L | H | M | Triangulate — if cadence + content + dispatch all working, root cause is non-comms; document and re-scope | Sponsor |
| R10 | Single-point-of-knowledge (Consultant departs without KT) | L | H | M | Phase-end KT sessions (Section 36); runbook + author guide deliverables | Sponsor + CTO |
| R11 | Client delay in counter-signature on Acceptance Notice | M | M | M | Deemed acceptance (Section 24.2) | Both |
| R12 | Late payment of milestone invoices | L | M | M | Net-15 + 1.5%/mo late fee + work-pause clause (Section 39) | Both |
| R13 | Data leak from sample / test data | L | H | M | Tokenised PII only in test data; least-privilege; audit logs (Section 20) | CTO + Consultant |
| R14 | Channel-provider contract terms shift between scoping and P5 | M | M | M | P5 plan re-baselined when contracts signed | CTO |
| R15 | Conflict of interest with Consultant’s other clients | L | M | L | Conflict declared at engagement start; non-solicit clause (Section 51) | Both |

PART X

Resourcing & Readiness

# 33. Effort Estimation

Effort is decomposed by phase and activity. Consultant-days are the basis for phase-milestone billing under Section 39. Reviewer-days are Client-internal time and are not billed by the Consultant.

## 33.1  Consultant effort

| Phase | Activity | Days |
| --- | --- | --- |
| P1 | Foundation: scaffolding, schemas, 5 skills, renderer, PH-03 walkthrough | 5 |
| P2 | PH library: 18 triggers, ~50 templates, spreadsheet import, review pack | 8 |
| P3 | INV (16) + INS (6) + OPS (6) + REG (3) triggers; HI variants; localisation queue | 7 |
| P4 | Lint engine: 30+ rules across 6 regimes; approval-gate enforcement; audit-trail export | 5 |
| P5 (gated) | MSG91/Karix/Gupshup integration; WA BSP integration; dispatch + receipts | 10 |
| Total — Core (P1–P4) |  | 25 days |
| Total — incl. P5 |  | 35 days |

## 33.2  Client reviewer effort (informational)

| Reviewer | Activity | Days |
| --- | --- | --- |
| CX Head | Brand voice, audience map, trigger taxonomy, review queue | 3 |
| Compliance Lead | Disclaimer set, lint-rule definition, review queue | 3 |
| Brand Reviewer | Per-template brand-voice sign-off (continuous) | 2 |
| CTO | Architecture, integrations, P5 channel-provider selection | 1 |
| Total reviewer effort |  | 9 days |

# 34. Resource Plan

## 34.1  Consultant resources

| Role | Allocation | Coverage | Phases |
| --- | --- | --- | --- |
| Engagement Lead / Solution Architect | Full-time during build (≈ 25 days) | Author, integrator, primary reviewer interface | P1–P4 (P5 if executed) |
| Backup contact (designated) | On call for continuity | Standby; no scheduled time | All phases |

## 34.2  Client resources

| Role | Allocation | Phase coverage |
| --- | --- | --- |
| CX Head (Brand + Audience) | ~4h/week | Continuous |
| Compliance Lead | ~4h/week | Continuous, peaks at P4 |
| Brand Reviewer | Continuous queue | P2–P4 |
| Operations Lead | ~3h/week | P2–P4 (spreadsheet import P2) |
| TPE Engineering pair | ~6h/week | Continuous, peaks at P1 and P5 |
| CTO | Phase-gate reviews + P5 selection | P1, gates, P5 |
| Sponsor (Founders) | Phase-gate reviews + CCB on Material+ CRs | Gates + CCB |

Concentration risk. The engagement runs through a single Consultant (Engagement Lead). This is appropriate at this scope but creates a single point of knowledge. Mitigations: (i) phase-end KT sessions per Section 36; (ii) all artefacts are in the Client repository, not in the Consultant’s private files; (iii) the runbook and author guide are written for a successor. The named backup contact provides continuity for unplanned absence.

# 35. Operational Readiness & Go-Live Criteria

“Go-live” is reached at the end of P4 for the library and lint capability. P5 carries an additional dispatch go-live, gated on its own readiness checklist.

## 35.1  Phase-by-phase readiness checklist

| Phase | Readiness items |
| --- | --- |
| P1 → P2 ready | Repo accessible to TPE Eng; 5 skills install cleanly; PH-03 walkthrough recorded; YAML schemas reviewed and signed off. |
| P2 → P3 ready | All 18 PH triggers authored and approved; ~50 templates active; spreadsheet import diff report shared; CX Head signed off on PH library. |
| P3 → P4 ready | INV/INS/OPS/REG triggers authored; HI variants exist for all PH-facing templates; localisation queue empty. |
| P4 go-live | 30+ lint rules active; approval gate enforced; audit-trail export reconciles to Git history; compliance reference card produced. |
| P5 go-live (if executed) | Channel-provider sandbox green; DLT IDs registered; WA BSP templates approved; dry-run dispatches succeed; production cutover plan signed off. |

## 35.2  Go-live decision authority

| Decision body | Sponsor + CTO + Compliance + CX (consensus) |
| --- | --- |
| Decision evidence | Phase-gate review pack + Acceptance Notice (Section 24) |
| Roll-back trigger | Sev-1 defect within 24h of go-live |
| Roll-back procedure | Revert to prior commit; preserve audit; post-mortem within 5 business days |

# 36. Knowledge Transfer & Training Plan

Knowledge transfer is engineered, not aspirational. Each phase ends with a recorded walk-through; the artefacts (runbook, author guide, compliance reference) are part of the deliverable set under Section 23. The intent is that a successor — Consultant or Client-hired — can operate the system without further support after a one-week onboarding.

## 36.1  Training tracks

| Audience | Format | Duration | Materials |
| --- | --- | --- | --- |
| Template authors (CX, Compliance, Brand) | Live + recorded walk-through | 2h × 2 sessions | Author guide + 10 worked examples |
| Reviewers (Compliance + Brand) | Live + recorded | 1h | Reviewer checklist + lint-rules reference |
| TPE Eng (build pair) | Pair sessions throughout build | Continuous | Repo + skill .md files |
| Operations (cadence + escalation) | Live + recorded | 1h | Operations runbook |
| Sponsor / CTO | Briefing | 30 min | Single-page summary + Q&A |

## 36.2  Acceptance of KT

KT is deemed accepted when (a) the recorded sessions are filed in the Client repository; (b) at least one Client author has produced and approved a template end-to-end without Consultant assistance; and (c) the runbook and author guide are signed off by CX Head.

# 37. Post-Implementation Support & Maintenance

After P4 acceptance, the engagement enters a defined post-implementation support window. Support is bounded in time, scope and effort. Beyond this window, any continued engagement is subject to a renewal SOW or an ad-hoc statement of work for time and materials at the rate card (Section 41).

## 37.1  Support window

| Duration | 12 calendar months from P4 acceptance |
| --- | --- |
| Scope | Defect remediation per severity SLAs (Section 21.3); minor template additions ≤ 2 days; quarterly compliance-rule review |
| Out of scope | New audiences, new triggers, new channels, new languages — these are change orders or new SOWs |
| Effort envelope | Aggregate cap of 5 consultant-days per quarter; carries over within calendar quarter only |
| Response SLA | Per Section 21.3 by severity |
| Charges | Included in Phase 4 milestone for the first quarter; subsequent quarters at quarterly retainer per Section 41 |

## 37.2  Hand-off plan

- Final runbook update; final lint-rule snapshot; per-quarter audit export.

- Designated Client successor named at P4 acceptance — KT (Section 36) is targeted to that named successor.

- Repository ownership transferred to Client GitHub organisation; Consultant retains read-only access for support window only.

- End-of-window letter: open items, recommended improvements, residual risks.

PART XI

Commercial Terms

# 38. Charges & Engagement Model

The commercial structure is hybrid by design: phase-milestone fixed-price billing for the agreed core scope (Phases 1–4) and time-and-materials at the rate card for any change orders or out-of-scope work (Section 41). Phase 5, if executed, is billed as a single fixed-price milestone on completion.

## 38.1  Engagement model

| Element | Treatment |
| --- | --- |
| Engagement type | Hybrid: phase-milestone fixed-price (P1–P4 and P5) + T&M for change orders |
| Currency | Indian Rupees (INR / ₹). All amounts exclusive of GST and statutory taxes |
| Billing cycle | Per phase milestone (Section 39); change orders monthly in arrears |
| Payment terms | Net 15 days from invoice receipt by the Client |
| Late payment | 1.5% per month or part thereof on overdue amounts; Consultant’s right to suspend work after 30 days overdue (Section 39.4) |
| Mode of payment | Direct bank transfer to the Consultant’s nominated account; UPI / NEFT / RTGS |

## 38.2  Day rate and contract value

The day rate below is the basis for change orders and for the derivation of phase milestone amounts. It is set at signing and held for the duration of this SOW; revisions follow the Change Management Process (Section 27).

| Item | Quantum | Notes |
| --- | --- | --- |
| Standard day rate (Principal Engineer / Solution Architect) | INR 35,000 per consultant-day | Indicative anchor for engagements of this profile in BFSI India 2026; subject to negotiation at signing |
| Working day definition | 8 working hours; IST business days | Half-day minimum on change orders |
| Core consultant effort | 25 days (Phases 1–4) | Per Section 33 |
| Core fixed price (P1–P4) | INR 8,75,000 | 25 × INR 35,000 — distributed across milestones in Section 39 |
| Phase 5 effort (gated) | 10 days | Triggered only on signed Phase 5 schedule |
| Phase 5 fixed price (gated) | INR 3,50,000 | Single milestone on completion |
| GST | 18% additional | On every invoice; included on tax invoice; subject to applicable rate at time of invoice |
| TDS | Applicable rate | Client deducts at source per Income Tax Act; TDS certificate (Form 16A) issued quarterly |

Day rate is indicative. INR 35,000/day is the anchor used to compute the milestones below. The Parties may agree a different rate at signing — if so, the milestone amounts in Section 39 are recomputed pro-rata against the agreed rate, with the milestone percentages held constant. The Consultant must confirm the final rate before counter-signature.

# 39. Payment Schedule & Milestones

Payments are tied to phase acceptance under Section 24. A milestone invoice is raised on the date acceptance is recorded — express or deemed — and is payable on Net 15 terms. Mobilisation is invoiced on counter-signature of this SOW. GST is added to every invoice at the rate applicable on the invoice date.

## 39.1  Core milestones (P1–P4)

| # | Milestone | Trigger | % | Amount (INR) |
| --- | --- | --- | --- | --- |
| M0 | Mobilisation advance | Counter-signature of this SOW | 20% | 1,75,000 |
| M1 | Phase 1 acceptance | P1 accepted under Section 24 | 20% | 1,75,000 |
| M2 | Phase 2 acceptance | P2 accepted under Section 24 | 25% | 2,18,750 |
| M3 | Phase 3 acceptance | P3 accepted under Section 24 | 20% | 1,75,000 |
| M4 | Phase 4 acceptance | P4 accepted under Section 24 | 15% | 1,31,250 |
| Total — Core (P1–P4) |  |  |  | ₹ 8,75,000 |

## 39.2  Phase 5 milestone (gated, optional)

Phase 5 is executed only on signature of a separate Phase 5 schedule referencing this SOW. The schedule confirms the channel-provider selection, dispatch scope, and any commercial adjustments. Until the Phase 5 schedule is signed, no commitment, no effort and no charge applies to Phase 5.

| # | Milestone | Trigger | % | Amount (INR) |
| --- | --- | --- | --- | --- |
| M5 | Phase 5 acceptance | P5 accepted under Section 24 (sandbox + production cutover sign-off) | 100% of P5 | 3,50,000 |

## 39.3  Total contract value summary

| Component | Amount (INR, ex-GST) | Including GST @ 18% |
| --- | --- | --- |
| Core (P1–P4) | 8,75,000 | 10,32,500 |
| Phase 5 (gated, optional) | 3,50,000 | 4,13,000 |
| Aggregate (if P5 executed) | 12,25,000 | 14,45,500 |
| Estimated reimbursable expenses (cap) | Pre-approved actuals only — see Section 40 | — |

## 39.4  Late payment, suspension, and disputed amounts

- Invoices are payable Net 15 from receipt. Receipt is presumed on the next business day after email transmission to the Client’s designated finance contact.

- Overdue amounts attract simple interest at 1.5% per month (or part thereof), accruing daily, from the original due date until paid. The Consultant may waive interest in writing; silence is not waiver.

- If any invoice remains unpaid for more than 30 calendar days after its due date, the Consultant may, on 7 calendar days’ written notice, suspend further work. Suspension does not constitute termination, does not relieve the Client of payment for accrued work, and extends every applicable phase SLA on a day-for-day basis.

- If the Client disputes any portion of an invoice in good faith, the Client must pay the undisputed portion on the original due date and notify the Consultant of the disputed portion in writing with specific reasons within 10 business days of invoice receipt. The disputed portion is held pending resolution under Section 50; failure to dispute within the 10-day window is deemed acceptance of the invoice.

- All charges, late fees and dispute mechanics survive termination of the engagement to the extent of work accrued before termination.

# 40. Invoicing, Taxes & Out-of-Pocket Reimbursements

## 40.1  Invoicing

| Invoice format | GST-compliant tax invoice; PDF emailed to Client’s designated finance contact |
| --- | --- |
| Invoice contents | Consultant name, address, PAN, GSTIN; SOW reference (TPE-COMMS-SOW-2026-001); milestone reference; consultant-day count; HSN/SAC code; CGST/SGST/IGST split; total amount; payment instructions; due date |
| Issue cadence | Milestone invoices on acceptance (Section 24); change-order invoices monthly in arrears; reimbursable invoices monthly in arrears |
| Currency | INR only |
| Designated finance contact | [Client to insert] — without this address, invoice receipt is on transmission to Client Sponsor |

## 40.2  Taxes

- All amounts in this SOW are exclusive of GST and any statutory taxes. The Consultant adds GST at the applicable rate (currently 18% under SAC 998313 for IT consulting, subject to GST Council revisions) on every invoice.

- The Client deducts Tax Deducted at Source (TDS) at the applicable rate on each invoice as required under the Income Tax Act, 1961. The Client issues TDS certificates (Form 16A) on a quarterly basis within statutory timelines.

- Each Party bears its own income tax obligations. Nothing in this SOW transfers any tax liability between the Parties.

- If GST law changes after signing such that the rate, classification or place-of-supply rules differ, the Parties act in good faith to align invoicing without altering the net amount due to the Consultant.

## 40.3  Out-of-pocket reimbursements

The engagement is delivered remotely by default. Where the Client requests on-site presence, the costs below are reimbursable on production of receipts and pre-approval. Reimbursements are charged at actuals; the Consultant adds no markup.

| Category | Treatment | Cap / norm |
| --- | --- | --- |
| Travel — air | Economy class within India; pre-approved | Lowest fare on direct route within ± 4h of preferred slot |
| Travel — rail | AC 2-tier or AC chair car; pre-approved | — |
| Local transport | Cab / metro at actuals | Standard ride-hail receipts |
| Hotel | Business-class equivalent; pre-approved | INR 6,500 per night excluding GST (norm; Client may approve higher for tier-1 metros) |
| Per diem (meals + incidentals) | Flat rate when traveling | INR 1,500 per day; no receipts required up to cap |
| Communication / tools | Not separately reimbursed | Included in day rate |
| Software licences purchased on Client’s behalf | At cost; Client to take direct title where possible | Pre-approval required |

## 40.4  Pre-approval and audit

- Reimbursable items above INR 5,000 require Client written pre-approval (email is sufficient). Items below this threshold may be approved retrospectively at the next reimbursement cycle.

- Reimbursable invoices are submitted monthly with copies of underlying receipts. The Client may audit reimbursable expenses for a period of 12 months from invoice date and dispute documented errors per Section 39.4.

- The Consultant maintains expense records for 7 years per the Income Tax Act.

# 41. Change Orders & Rate Card

Where a change request under Section 27 is classified as Material or Critical, or where work falls outside the scope defined in Section 11, a Change Order is raised. Change Orders are charged at the rate card below, billed monthly in arrears, and follow the same payment terms as milestone invoices.

## 41.1  Rate card

| Service | Unit | Rate (INR, ex-GST) |
| --- | --- | --- |
| Principal Engineer / Solution Architect (Consultant — Engagement Lead) | per consultant-day | 35,000 |
| Half-day engagement (minimum chargeable unit) | per half-day | 20,000 |
| Out-of-hours work (after 19:00 IST or weekends), pre-approved | per consultant-day | 52,500 (1.5×) |
| Public holiday work (India), pre-approved | per consultant-day | 70,000 (2×) |
| Quarterly retainer (post-implementation, beyond first quarter) | per quarter | 1,75,000 (5 days) |
| Ad-hoc advisory (single-session, scoped) | per session up to 2h | 10,000 |

## 41.2  Change Order procedure

- A Change Order is a written instrument that references this SOW, describes the change, states the effort estimate, the cost, and any timeline impact. It is signed by the Client Sponsor (or delegate) and the Consultant before work begins.

- Effort estimates on Change Orders are best-effort; if actual effort exceeds estimate by more than 25%, the Consultant must notify the Client and obtain written authorisation before continuing — failure to notify caps charges at the original estimate plus 25%.

- Change Orders are billed monthly in arrears at the rates above. They do not extend the original SOW automatically — every Change Order has its own start date, scope and end date.

- Reimbursable expenses on Change Orders follow Section 40.3.

PART XII

Legal & Contract Terms

# 42. Warranty & Service Standards

The Consultant warrants the standard of services and the period during which defects will be remedied at no charge. Beyond these warranties, no other warranty — express or implied — is given. This section does not limit any non-excludable consumer or statutory protection.

## 42.1  Service standard

The Consultant warrants that the services under this SOW will be performed in a workmanlike, professional manner, using personnel with the skill and experience reasonably required for engagements of this nature, and consistent with industry-standard practice for BFSI consulting in India.

## 42.2  Re-performance warranty

If, within 90 calendar days from acceptance of any deliverable under Section 24, the Client demonstrates that the deliverable materially fails to meet the acceptance criteria (Section 24.1) and the failure was not caused by Client modification or use outside agreed parameters, the Consultant will, at the Consultant’s option and at no additional charge, re-perform or remedy the deliverable. Re-performance is the Client’s sole and exclusive remedy under this warranty.

## 42.3  Disclaimer

Except for the warranties expressly stated in this Section 42 and any non-excludable warranty implied by law, the Consultant disclaims all other warranties, conditions, representations and terms — whether express, implied, statutory or otherwise — including any warranty of merchantability, fitness for a particular purpose, non-infringement, or that the deliverables will be uninterrupted, error-free or secure against unauthorised access. The Client acknowledges that the deliverables are tools that depend on Client data, Client systems, third-party providers and regulatory frameworks not within the Consultant’s control.

# 43. Limitation of Liability

This Section is a fundamental basis on which the Consultant has agreed the charges in Part XI. Without these limits, the charges would be materially higher. Any provision of this Section deemed unenforceable is to be construed to the maximum extent permissible by law.

## 43.1  Aggregate cap

Each Party’s aggregate liability arising out of or in connection with this SOW — whether in contract, tort (including negligence), under statute, or on any other basis — is capped at the total fees paid by the Client to the Consultant under this SOW in the twelve (12) months immediately preceding the event giving rise to the claim. Where the engagement has been in effect for less than twelve months, the cap is the total fees paid to date.

## 43.2  Exclusion of indirect damages

Neither Party is liable to the other for any indirect, incidental, special, consequential, exemplary or punitive damages, or for any loss of profits, loss of revenue, loss of business, loss of goodwill, loss of opportunity, loss of anticipated savings, loss of data, or cost of substitute services — whether or not the Party has been advised of the possibility of such damages — arising out of or in connection with this SOW.

## 43.3  Exceptions

The cap and exclusion in Sections 43.1 and 43.2 do not apply to: (a) breach of confidentiality obligations under Section 47; (b) infringement by either Party of the other’s intellectual property; (c) gross negligence, fraud or wilful misconduct; (d) liability that cannot be limited or excluded under applicable law; or (e) the Client’s obligation to pay charges due and undisputed under Part XI.

## 43.4  Allocation of risk

The Parties acknowledge that the limits in this Section reflect a deliberate allocation of risk consistent with the charges agreed and the scope of the engagement. Each Party has had the opportunity to obtain independent legal advice on this allocation.

# 44. Indemnification

Each Party indemnifies the other against specified third-party claims as set out below. Indemnification is the indemnified Party’s sole remedy for the matters covered.

## 44.1  Consultant indemnity — IP infringement

The Consultant will defend the Client against any third-party claim that the deliverables produced under this SOW, when used by the Client as contemplated in this SOW, infringe the copyright, trademark, registered design, or trade secret of that third party in India, and will pay any damages and costs finally awarded against the Client by a court of competent jurisdiction (or paid in settlement approved by the Consultant). The Consultant’s obligation under this Section 44.1 is conditional on the Client (i) notifying the Consultant in writing within 10 business days of becoming aware of the claim; (ii) giving the Consultant sole control of the defence and any settlement; and (iii) providing reasonable cooperation.

If a claim is made or, in the Consultant’s reasonable opinion, is likely to be made, the Consultant may, at its option: (a) procure the right for the Client to continue to use the deliverable; (b) replace or modify the deliverable to be non-infringing while preserving its functional equivalence; or (c) accept return of the deliverable and refund the corresponding portion of fees paid. The remedies in this Section 44.1 are the Client’s sole and exclusive remedies for any IP infringement claim.

## 44.2  Consultant indemnity exclusions

The Consultant has no obligation under Section 44.1 to the extent a claim arises from: (a) Client modification of the deliverable not authorised by the Consultant; (b) Client combination of the deliverable with software, data or processes not supplied by the Consultant where the claim would not have arisen but for the combination; (c) Client use outside the scope contemplated in this SOW; (d) Client failure to implement an updated, non-infringing version made available by the Consultant; or (e) materials, content, brand assets or templates supplied by the Client to the Consultant.

## 44.3  Client indemnity

The Client will defend the Consultant against any third-party claim arising from: (a) the Client’s misuse of the deliverables outside the scope contemplated in this SOW; (b) data, content, brand assets, customer lists or PII supplied by the Client to the Consultant being unlawful, infringing, or processed without lawful basis; (c) the Client’s breach of its obligations under DPDPA, IRDAI regulations or any other applicable law; or (d) the Client’s independent business decisions including selection of channel providers, registration of DLT entities, and decisions to dispatch any specific message. The same conditions and process as Section 44.1 apply, with roles reversed.

## 44.4  Mutual indemnity — confidentiality

Each Party indemnifies the other against direct losses arising from a breach of confidentiality obligations under Section 47 by the indemnifying Party or its personnel. Such losses are subject to Section 43.1 and are exceptions only to the extent stated in Section 43.3.

# 45. Insurance Requirements

The Consultant agrees to maintain insurance cover commensurate with the scope and risk of the engagement. The Client has the right to request a current certificate of insurance from each policy at any time during the term.

| Cover | Minimum sum insured | Notes |
| --- | --- | --- |
| Professional Indemnity (errors & omissions) | INR 1,00,00,000 (1 Crore) | Aggregate per policy year; covering services delivered under this SOW |
| Public Liability / Commercial General Liability | INR 50,00,000 (50 Lakh) | Per occurrence; covering on-site presence and equipment use |
| Cyber Liability (recommended, not mandatory in v1) | INR 50,00,000 (50 Lakh) | Where the Consultant handles Client PII at material volume |

## 45.1  General terms

- Coverage to be maintained continuously through the term of this SOW and for 12 months thereafter (run-off / extended reporting).

- Consultant to notify Client within 10 business days of any change that materially reduces cover, lapse of policy, or claim made against any policy that may impact the Client.

- Insurance does not cap, reduce or substitute for any liability under this SOW; it is additional to any contractual remedy.

- Where the Consultant operates as an individual rather than an entity, the Parties may at signing agree to substitute insurance with a higher liability cap under Section 43.1, by mutual written agreement on the schedule of definitions.

# 46. Term, Renewal & Termination

## 46.1  Term

This SOW takes effect on the Effective Date stated in Section 1 and continues until the later of: (a) acceptance of all in-scope deliverables under Section 24; and (b) the end of the post-implementation support window under Section 37 (12 calendar months from P4 acceptance), unless terminated earlier under this Section.

## 46.2  Renewal

This SOW does not auto-renew. Continuation of services beyond the Term — including additional phases, new audiences, new channels, ongoing managed services, or further support — requires either an executed Change Order (Section 41) or a new Statement of Work referencing the master engagement.

## 46.3  Termination for convenience

Either Party may terminate this SOW for convenience by providing 30 calendar days’ written notice to the other Party. On termination for convenience: (a) the Consultant ceases work in an orderly manner; (b) the Client pays for all consultant-days delivered up to the effective termination date plus any committed third-party costs the Consultant cannot mitigate; (c) any work-in-progress deliverables are handed over in their then-current state; and (d) the mobilisation advance is reconciled against work delivered, with any surplus refunded within 30 days.

## 46.4  Termination for material breach

Either Party may terminate this SOW for material breach if the other Party: (a) commits a material breach of this SOW capable of remedy and fails to remedy that breach within 15 calendar days of receiving written notice specifying the breach; (b) commits a material breach not capable of remedy; or (c) becomes insolvent, enters into liquidation (other than for solvent reconstruction), has a receiver appointed, files for protection from creditors, or ceases or threatens to cease carrying on business.

“Material breach” includes, without limitation: persistent failure to meet phase acceptance criteria after rework cycles permitted under Section 24.3; non-payment of an undisputed invoice for more than 60 calendar days past due; breach of confidentiality obligations under Section 47; breach of data-protection obligations under Section 48; and any conduct by either Party’s personnel that creates a material regulatory or reputational risk to the other Party.

## 46.5  Effects of termination

| Effect | Description |
| --- | --- |
| Charges accrued | Client pays Consultant for all services delivered up to the effective termination date, including any phase milestone where acceptance criteria have substantially been met |
| Hand-over | Consultant provides reasonable hand-over of in-progress work; final hand-over invoice may include up to 2 days of effort at the rate card |
| Client property | Consultant returns or destroys Client confidential information per Section 47.5 |
| Repository ownership | Repository ownership transfers to Client (where not already vested) as soon as accrued and disputed amounts are settled |
| Survival | Sections 1, 2, 24 (for accrued acceptance), 38–41 (for accrued payments), 42–51 survive termination |
| No relief from accrued obligations | Termination does not relieve either Party of any obligation accrued before the effective date |

# 47. Confidentiality, IP & Data Ownership

## 47.1  Confidential information

“Confidential Information” means any non-public information disclosed by one Party to the other in connection with this SOW, in any form, that is identified as confidential or that a reasonable person would understand to be confidential. It includes Client business plans, customer data, operational metrics, partner relationships, internal documents, and the Consultant’s methodologies, prompt suites, skill code, and pricing.

## 47.2  Obligations

- Each Party will hold the other’s Confidential Information in strict confidence; will use it only for the purpose of performing this SOW; and will protect it with at least the same degree of care it uses for its own confidential information of like importance, and in any event no less than reasonable care.

- Disclosure is permitted only to the receiving Party’s personnel, advisers and subcontractors who have a need to know, who are bound by written confidentiality obligations no less protective than this Section, and for whose acts and omissions the receiving Party remains responsible.

- Confidential Information does not include information that: (a) is or becomes publicly known other than through a breach of this Section; (b) was known to the receiving Party before disclosure without obligation of confidence; (c) is independently developed by the receiving Party without use of the other’s Confidential Information; or (d) is received from a third party without obligation of confidence and without breach of any duty owed to the disclosing Party.

- If the receiving Party is compelled by law, court order or regulator to disclose Confidential Information, it will (where lawful) notify the disclosing Party in advance and disclose only the minimum necessary.

## 47.3  Data classification

| Class | Examples | Handling |
| --- | --- | --- |
| PII — High | ph_name, phone, email, PAN, bank_last4 | Tokenised in templates; never logged raw; audit-masked |
| PII — Medium | policy_no, premium_amount, due_date | Encrypted at rest; least-privilege access |
| Operational | trigger_id, template_id, status | Internal use; safe to log |
| Brand confidential | Disclaimer texts, brand-voice rules | Internal-only; no external sharing |
| Consultant proprietary | Skill code, methodologies, prompt suites | Consultant retains; licensed to Client per 47.4 |

## 47.4  Intellectual property

Subject to full payment of the charges due under Part XI, all rights, title and interest in the deliverables specifically created for the Client under this SOW (including the Client-specific trigger catalogue, templates, compliance-rule definitions tailored to Client regimes, and Client-specific runbooks and documentation) vest in the Client on acceptance under Section 24.

The Consultant retains all rights, title and interest in: (a) generic methodologies, frameworks, prompt patterns, skill scaffolds, slash-command structures, lint engines and authoring tools that are not Client-specific and that the Consultant brings to the engagement or develops independently of Client confidential information; (b) generic best-practice content that is not specific to TPE’s business; and (c) skills, knowledge, and experience gained during the engagement. The Consultant grants the Client a perpetual, irrevocable, royalty-free, worldwide, non-exclusive licence to use, reproduce, modify and create derivative works of items in (a) and (b) to the extent embedded in the Client deliverables.

Open-source components incorporated in any deliverable are governed by their applicable licences. The Consultant identifies material open-source components in the runbook (Section 23 deliverables) and will not knowingly incorporate copyleft-licensed components that would impose additional obligations on the Client deliverables without prior written approval.

## 47.5  Return or destruction

On termination of this SOW or on the disclosing Party’s written request, the receiving Party will, within 30 calendar days, return or destroy (at the disclosing Party’s option) all Confidential Information of the disclosing Party in the receiving Party’s possession or control, and certify the same in writing. The receiving Party may retain copies required by law, by professional standards, or for archival purposes only — such retained copies remain subject to the confidentiality obligations of this Section.

## 47.6  Duration

Confidentiality obligations under this Section survive termination of this SOW for: (a) 5 years from termination, in respect of general business and operational information; (b) indefinitely, in respect of trade secrets and personal data; and (c) the period required by law, in respect of regulated information.

# 48. Data Protection (DPDPA) & Data Processing Agreement

To the extent the Consultant processes personal data on behalf of the Client in performing this SOW, the Parties’ respective obligations under the Digital Personal Data Protection Act, 2023 (DPDPA) are set out in a separate Data Processing Agreement (DPA) executed contemporaneously with, or before, this SOW. The DPA forms part of the contractual framework between the Parties; in case of conflict between this SOW and the DPA on data-protection matters, the DPA prevails.

## 48.1  Roles

| Data Fiduciary (Controller) | The Client, in respect of all personal data of policyholders, investors, partners, employees and other data principals processed in connection with the Client’s business |
| --- | --- |
| Data Processor | The Consultant, in respect of any personal data processed on behalf of the Client during this engagement |
| Sub-processors | Any third party engaged by the Consultant to process Client personal data; engagement requires Client prior written consent and equivalent data-protection obligations |

## 48.2  Core obligations

- The Consultant processes Client personal data only on the documented instructions of the Client, including with regard to transfers outside India to the extent permitted by DPDPA.

- The Consultant ensures that personnel authorised to process Client personal data are bound by appropriate confidentiality obligations and have received reasonable data-protection training.

- The Consultant assists the Client, taking into account the nature of processing and the information available, in: (a) responding to data-principal requests under DPDPA; (b) ensuring security of processing; (c) notifying personal-data breaches; and (d) consulting the Data Protection Board of India where required.

- The Consultant notifies the Client without undue delay (and in any event within 24 hours) of becoming aware of any personal-data breach affecting Client personal data.

- On end of processing services, the Consultant deletes or returns all Client personal data, at the Client’s choice, save where retention is required by law.

## 48.3  PII handling within this engagement

In practice, this engagement does not require the Consultant to hold production PII at scale. Sample data used for design, render goldens and tests is tokenised PII (synthetic or anonymised) provided by the Client. Where genuine PII is exposed during pair-debugging or production-incident triage, it is handled per Section 20 (Security & Privacy Framework) and is not retained beyond the immediate triage.

# 49. Force Majeure

Neither Party is liable for any delay or failure to perform any obligation under this SOW (other than the obligation to pay money due) where the delay or failure results from a Force Majeure Event, provided the affected Party (a) notifies the other Party promptly with details and expected impact; (b) takes reasonable steps to mitigate; and (c) resumes performance as soon as reasonably practicable.

## 49.1  Force Majeure Events

“Force Majeure Event” means any event beyond the reasonable control of the affected Party, including: acts of God; natural disasters (earthquake, flood, fire, cyclone); epidemics and pandemics, and public-health measures imposed in response; war, terrorism, civil unrest and acts of public enemies; acts or omissions of government, regulator, court or other competent authority including new laws or restrictions; failure or unavailability of public utilities (power, water) for a sustained period; nationwide strike or lockout not localised to one Party. The following are expressly not Force Majeure Events: (i) ordinary internet outages affecting an individual Party’s premises; (ii) the affected Party’s own internal labour disputes; (iii) inability to pay; (iv) failure of an affected Party’s subcontractor or supplier unless that failure itself qualifies as a Force Majeure Event.

## 49.2  Termination for prolonged Force Majeure

If a Force Majeure Event continues to prevent material performance for more than 30 consecutive calendar days, either Party may terminate this SOW by written notice with no liability beyond charges accrued to the date of the Event. Section 46.5 (Effects of termination) applies.

# 50. Governing Law & Dispute Resolution

## 50.1  Governing law

This SOW, and any non-contractual obligation arising in connection with it, is governed by and construed in accordance with the laws of the Republic of India, without giving effect to any conflict-of-laws principles that would result in the application of the laws of another jurisdiction.

## 50.2  Tier 1 — Negotiation

The Parties will attempt in good faith to resolve any dispute arising out of or in connection with this SOW (“Dispute”) by negotiation between the Client Sponsor and the Consultant Engagement Lead. Either Party may initiate negotiation by written notice to the other identifying the Dispute. If the Dispute is not resolved within 30 calendar days of the notice, either Party may proceed to Tier 2.

## 50.3  Tier 2 — Arbitration

Any Dispute not resolved under Section 50.2 will be referred to and finally resolved by arbitration conducted under the Arbitration and Conciliation Act, 1996 (as amended), and the rules thereunder. The arbitration will be conducted by a sole arbitrator appointed by mutual agreement of the Parties; failing such agreement within 15 business days of the request for arbitration, the appointment will be made in accordance with the Act. The seat and venue of arbitration is New Delhi, India. The language of arbitration is English. The award is final and binding on the Parties.

## 50.4  Jurisdiction

Subject to Section 50.3, the courts at New Delhi have exclusive jurisdiction in respect of any matter not required to be submitted to arbitration, including applications for interim relief and enforcement of an arbitral award.

## 50.5  Continued performance

During the pendency of any Dispute, both Parties continue to perform their obligations under this SOW (other than the disputed obligations) and the Client continues to pay all undisputed amounts when due.

## 50.6  Equitable relief

Notwithstanding Sections 50.2 and 50.3, either Party may at any time apply to a court of competent jurisdiction for interim or injunctive relief to protect its confidential information, intellectual property, or to enforce payment obligations, without first exhausting the negotiation and arbitration tiers.

# 51. General Provisions

## 51.1  Independent contractor

The Consultant is engaged as an independent contractor. Nothing in this SOW creates a partnership, joint venture, agency, employer-employee, or fiduciary relationship between the Parties. Neither Party has authority to bind the other or to incur any obligation on behalf of the other except as expressly stated in this SOW. The Consultant is solely responsible for any income tax, professional tax, social-security or other statutory contributions arising from the charges payable under this SOW.

## 51.2  Non-solicitation

During the Term and for 12 calendar months thereafter, neither Party will, directly or indirectly, solicit for employment or engagement any employee or contractor of the other Party who was actively involved in this engagement, except: (a) through general public advertisements not specifically targeted at such persons; or (b) with the prior written consent of the other Party. Hire of an applicant who responds to a general public advertisement is permitted.

## 51.3  Anti-bribery and anti-corruption

Each Party will comply with all applicable anti-bribery and anti-corruption laws, including the Prevention of Corruption Act, 1988 (India). Neither Party will offer, give, or accept any bribe, kickback or improper benefit in connection with this SOW. Each Party may terminate this SOW immediately on written notice for breach of this Section, treating it as material breach not capable of remedy under Section 46.4.

## 51.4  Severability

If any provision of this SOW is held by a court or arbitrator of competent jurisdiction to be invalid or unenforceable, the remainder of the SOW remains in full force and effect, and the Parties will negotiate in good faith to replace the invalid or unenforceable provision with a valid and enforceable one that achieves the original commercial intent as closely as possible.

## 51.5  Entire agreement

This SOW (together with any Change Orders, the Phase 5 schedule if executed, and the DPA referenced in Section 48) constitutes the entire agreement between the Parties with respect to its subject matter and supersedes all prior or contemporaneous proposals, negotiations, understandings, and agreements (whether written or oral). The Parties have not relied on any statement, representation, assurance or warranty not expressly set out in this SOW.

## 51.6  Amendment

No amendment, modification or waiver of any provision of this SOW is effective unless in writing and signed by an authorised representative of each Party. Email exchanges, even if explicit, do not amend this SOW unless the email is countersigned by an authorised representative or attaches a signed amendment instrument.

## 51.7  Notices

Any notice required or permitted under this SOW must be in writing and will be deemed to have been duly given: (a) on personal delivery to the addressee; (b) on delivery confirmation if sent by registered post; or (c) on transmission confirmation if sent by email to the address designated by the Party. Each Party may change its notice address by written notice to the other.

| Notices to Client | [Client to insert: name, address, email of designated notice recipient] |
| --- | --- |
| Notices to Consultant | [Consultant to insert: name, address, email of designated notice recipient] |

## 51.8  Assignment

Neither Party may assign, transfer or sub-contract any of its rights or obligations under this SOW without the prior written consent of the other Party, such consent not to be unreasonably withheld. Notwithstanding the foregoing: (a) the Consultant may sub-contract specific tasks to qualified personnel provided the Consultant remains primarily responsible to the Client and obtains equivalent confidentiality and IP protections; and (b) either Party may assign this SOW to a successor in connection with a merger, acquisition, or sale of substantially all of its assets, on written notice to the other Party.

## 51.9  Counterparts and electronic signatures

This SOW may be executed in counterparts, each of which is an original and which together constitute one and the same instrument. Electronic signatures (including DSC under the Information Technology Act, 2000) are valid and binding.

## 51.10  No third-party beneficiaries

This SOW is for the benefit of the Parties and their respective successors and permitted assigns. It does not create any rights or remedies in any third party.

## 51.11  Publicity

The Consultant may, with the Client’s prior written approval (not to be unreasonably withheld for general capability marketing), reference the Client’s name and a high-level description of the engagement on the Consultant’s website and proposals. The Consultant will not disclose specific commercial terms, customer data, or operational metrics without express written consent of the Client. The Client may reference the Consultant similarly, subject to the same constraints.

PART XIII

Reference & Sign-off

# 52. Glossary

Defined terms used in this SOW. Where a term is not defined here but is in capitalised form, its meaning is taken from the relevant statute or industry standard.

| Term | Meaning |
| --- | --- |
| BSP | Business Solution Provider — Meta-authorised reseller for WhatsApp Business API (e.g. MSG91, Karix, Gupshup) |
| CCB | Change Control Board — the cross-party body that decides on Material and Critical change requests (Section 27.2) |
| CR | Change Request — a formal proposal to alter the scope, effort, timeline or terms of this SOW (Section 27) |
| DLT | Distributed Ledger Technology — the TRAI mandate for SMS sender registration in India |
| DPA | Data Processing Agreement — the separate agreement governing personal-data processing (Section 48) |
| DPDPA | Digital Personal Data Protection Act, 2023 — India’s primary data-protection statute |
| DSC | Digital Signature Certificate — issued under the Information Technology Act, 2000 |
| FATCA | Foreign Account Tax Compliance Act — US legislation requiring reporting on US-person investors |
| IRDAI | Insurance Regulatory and Development Authority of India |
| MIS Pipeline | TPE’s existing automated batch-process generating monthly remittance attachments to insurer partners (used by trigger INS-02) |
| NPV | Net Present Value |
| OOP | Out-of-Pocket — reimbursable expenses (Section 40.3) |
| PII | Personally Identifiable Information |
| RACI | Responsible / Accountable / Consulted / Informed (Section 25) |
| RCS | Rich Communication Services — a SMS-successor messaging standard |
| RPO / RTO | Recovery Point Objective / Recovery Time Objective — backup-recovery targets (Section 20) |
| SAR | Subject Access Request — a data-principal request under DPDPA |
| Sev-1 / Sev-2 / Sev-3 / Sev-4 | Defect severity levels (Section 21.3) |
| SLA | Service Level Agreement (Section 28) |
| SOW | Statement of Work — this document |
| T&M | Time and Materials — billing model based on consultant-days at rate-card rates (Section 41) |
| TDS | Tax Deducted at Source — under the Income Tax Act, 1961 |
| TPE | The Policy Exchange — operating brand of Fairvalue Insuretech Pvt. Ltd., the Client |
| TRAI | Telecom Regulatory Authority of India |
| WhatsApp BSP category | Marketing / Utility / Authentication — Meta’s template categorisation that gates send eligibility |

# 53. References

Sources and reference frameworks consulted in preparing this SOW. References are non-exhaustive and are provided for traceability; the Parties’ obligations are governed by the body of this SOW and applicable law as in force from time to time.

## 53.1  Statutes and regulations

- Information Technology Act, 2000 (India), and the Information Technology (Reasonable Security Practices) Rules, 2011.

- Digital Personal Data Protection Act, 2023 (India).

- Insurance Act, 1938; Insurance Regulatory and Development Authority Act, 1999; relevant IRDAI regulations and circulars in force.

- Income Tax Act, 1961 (TDS, statutory documentation).

- Goods and Services Tax (Compensation to States) Act, 2017; Central / State / Integrated Goods and Services Tax Acts, 2017.

- Telecom Regulatory Authority of India Act, 1997; TRAI Telecom Commercial Communications Customer Preference Regulations, 2018 (DLT framework).

- Arbitration and Conciliation Act, 1996 (as amended).

- Indian Contract Act, 1872; Sale of Goods Act, 1930.

- Prevention of Corruption Act, 1988.

## 53.2  Industry standards and guidance

- WhatsApp Business Solution Terms; Meta Business Messaging policies (template categories: Marketing / Utility / Authentication).

- ISO/IEC 27001:2022 — Information security management (referenced for Section 20 controls).

- OWASP ASVS — Application Security Verification Standard (where relevant to renderer code).

## 53.3  Internal references

- TPE current message templates spreadsheet (provided by Client at scoping).

- Existing MIS Pipeline runbook (used by trigger INS-02).

- Brand voice samples and style guide (Client).

# 54. Sign-off

In witness of the terms set out in this Statement of Work, the duly authorised representatives of the Parties have signed below on the dates indicated. By signing, each Party represents that it has reviewed this SOW in full, that it has had the opportunity to obtain independent advice, and that the person signing has authority to bind the Party named.

This Statement of Work — Document ID TPE-COMMS-SOW-2026-001, Version 3.0 — comprises 54 sections in 13 Parts and is incorporated in full by signature.

| FOR THE CLIENT | FOR THE CONSULTANT |
| --- | --- |
| PRIMARY SIGNATORY Fairvalue Insuretech Pvt. Ltd. Authorised representative (operating as “The Policy Exchange”), Noida, UP, India Signature: __________________________________ Name: ____________________________________ Title: ____________________________________ Date: ____________________________________ Place: ____________________________________ | PRIMARY SIGNATORY Ashish Kumar Satyam Independent Consultant — Principal Engineer & Solution Architect BFSI & Insurtech Signature: __________________________________ Name: ____________________________________ Title: ____________________________________ Date: ____________________________________ Place: ____________________________________ |

### Counter-signatures (for Client internal endorsement)

The signatures below are for internal endorsement and document control only. They do not constitute additional contracting parties; the contractual signatories are those in the table above.

| Endorser role | Name | Signature | Date |
| --- | --- | --- | --- |
| Chief Technology Officer | _____________________ | _____________________ | _______ |
| Head of Compliance | _____________________ | _____________________ | _______ |
| Head of Customer Experience | _____________________ | _____________________ | _______ |

Effective date. This SOW takes effect on the latest of the dates shown in the FOR THE CLIENT and FOR THE CONSULTANT signature blocks above. The Effective Date is recorded in Section 1 once both signatures are complete.