THE POLICY EXCHANGE (FAIRVALUE INSURETECH PVT. LTD.)

PROJECT STATUS DOCUMENT

TPE Communication System

Stakeholder review — post sandbox-3.15-primary pivot (2026-05-01)

| 17/49 Workflows live | 32 Workflows pending | 3 Risks open | 1 Major pivot done |
| --- | --- | --- | --- |

Document metadata

| Document ID | TPE-COMMS-STATUS-2026-002 |
| --- | --- |
| Version | 2.0 |
| Date issued | 01 May 2026 |
| Prepared by | Ashish Kumar Satyam · TechDigital WishTree |
| Prepared for | The Policy Exchange |
| Audience | Stakeholders, leadership, audit committee |
| Classification | Internal / Confidential |
| Review cycle | Quarterly (next: Aug 2026) |

INTERNAL / CONFIDENTIAL — DO NOT REDISTRIBUTE

1.  Document Information

| Attribute | Value |
| --- | --- |
| Document name | TPE Communication System — Project Status Document |
| Document ID | TPE-COMMS-STATUS-2026-002 |
| Version | 2.0 |
| Date issued | 01 May 2026 |
| Owner | Ashish Kumar Satyam, TechDigital WishTree |
| For | The Policy Exchange (Fairvalue Insuretech Pvt. Ltd.) |
| Stakeholders | CTO, Compliance Lead, Engineering Lead, CX Lead, Operations Lead, Infrastructure Lead, Quality Lead |
| Classification | Internal / Confidential |
| Distribution | Project Owner + named stakeholders only |
| Approval required | Project Owner (CTO) sign-off before next phase kickoff |

2.  Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | 27 Apr 2026 | Ashish Kumar Satyam | Initial status report — pre-pivot. Captured Phase 1 plan + Charter alignment. |
| 1.5 | 30 Apr 2026 | Ashish Kumar Satyam | Mid-pivot interim — sandbox 3.15 deployed alongside live 2.3.0 for evaluation. |
| 2.0 | 01 May 2026 | Ashish Kumar Satyam | Post-pivot — sandbox 3.15 promoted to primary, TPE Admin sunsetted, 17 Charter workflows operational on sandbox with end-to-end MSG91+ICPaaS verified. |

3.  Executive Summary

The TPE Communication System completed its Phase 1 architectural pivot on 2026-05-01. The Novu Community Edition 3.15.0 sandbox dashboard at port 8080 is now the canonical operator surface for the operations team, replacing the custom-built TPE Admin Next.js application that was originally planned. The pivot was driven by the team's preference for the standard Novu UI over the custom admin ("we have to use the novu FE") and was executed without disruption to the live 2.3.0 stack, which remains running for redundancy.

Operationally, 17 of 49 Charter §4.3 lifecycle workflows are now live on the sandbox 3.15 stack with end-to-end MSG91 SMS + ICPaaS WhatsApp dispatch verified via the PH-02 OTP smoke trigger (transactionId txn_69f458d8shgs5i2ntcjh, MSG91 v5/Flow HTTP 200, ICPaaS wamid issued). The remaining 32 workflows are pending Phase 2-3 implementation by the engineering team.

The architectural rule established at this pivot — code-first authoring only, no Studio UI workflow creation — closes a compliance gap: every workflow change now flows through GitHub PR review, which keeps the Charter §E1 mandate ("all 49 lifecycle triggers live as Novu workflows in production, versioned in source control, pass compliance middleware CI gate, reviewable by CX/Compliance leads before merge") achievable in practice. Three open risks require leadership attention: (1) leaked private keys in a sister repository discovered during this session's audit, (2) MSG91 single-vendor concentration risk for SMS, and (3) email channel deferred indefinitely pending SES provisioning decision.

4.  Dashboard View

Headline status across project areas:

| Workflow delivery (17/49) | ● On track for Phase 1 |
| --- | --- |
| Sandbox 3.15 stack stability | ● Stable, all containers healthy |
| Live 2.3.0 stack | ● Running, de-emphasised |
| Code-first authoring rule | ● Established, enforced |
| MSG91 SMS dispatch | ● Verified end-to-end |
| ICPaaS WhatsApp dispatch | ● Verified end-to-end |
| Email channel (SES) | ● Deferred — not configured |
| Push channel (FCM/APNs) | ● Out of Phase 1 scope |
| Compliance middleware lint | ● ≥30 rules in CI gate |
| DLT template registration | ● 7 templates registered with MSG91 |
| Operator UI handover | ● Complete — Sandbox Dashboard is primary |
| video-kyc-webrtc secret leak | ● Open — rotation required |
| MSG91 single-vendor risk | ● Open — Gupshup fallback planned |
| Charter §E1 (49 workflows live) | ● 17/49 — 35% progress |

4.1  Phase 1 metrics

| 17 Workflows live | 4 Channels wired | 3 Compliance certs | 0 Production incidents |
| --- | --- | --- | --- |

5.  Completed Work

| Feature / Workstream | Description | Version | Completion Date |
| --- | --- | --- | --- |
| Track B deployment (live 2.3.0) | Single-VPS Docker Compose stack on Mumbai VPS | v1.0 | Apr 2026 |
| Bridge dispatch architecture | Custom step.custom + dispatch.ts pattern; MSG91+ICPaaS providers | v1.0 | Apr 2026 |
| 17 Charter §4.3 workflows authored | PH-02..17 + INV-02..12 in TypeScript code-first | v1.0 | Apr 2026 |
| DLT template registration | 7 MSG91 SMS templates approved + wired to env vars | v1.0 | Apr 2026 |
| Channel-matrix-by-stage pattern | Cadence-driven workflows: INV-08 / PH-15 / INV-11 | v1.0 | Apr 2026 |
| Sandbox 3.15 deployment | Side-by-side eval at :8080 / :8081 / :8083 | v1.0 | 30 Apr 2026 |
| Workflow wipe + re-sync | Both live 2.3.0 + sandbox 3.15 wiped and re-synced from Bridge code | — | 1 May 2026 |
| Sandbox 3.15 promoted to PRIMARY | TPE Admin sunsetted; next-bridge wired with real MSG91+ICPaaS creds | v2.0 | 1 May 2026 |
| End-to-end PH-02 smoke verification | MSG91 v5/Flow HTTP 200; ICPaaS wamid issued | v2.0 | 1 May 2026 |
| GitHub repo published | https://github.com/aksatyamtpe/tpe-novu — 188 files initial commit | v2.0 | 1 May 2026 |
| Operator Manual (Doc B) | 60 KB DOCX, 15 sections, daily reference for ops team | v1.0 | 1 May 2026 |
| Project Status Document (THIS doc) | 18-section enterprise master document | v2.0 | 01 May 2026 |

6.  Work in Progress

| Feature / Workstream | Description | Owner | Expected Completion |
| --- | --- | --- | --- |
| Pivot ADR (Doc C) | Architecture Decision Record for the 2026-05-01 pivot | Engineering Lead | 1-2 May 2026 |
| video-kyc-webrtc key rotation | Phase 1 of secret-leak remediation (GoDaddy wildcard, eKYC SSH, bulk-import SSH) | Infrastructure Lead | Within 1 week |
| Drift-check script | Compare Mongo workflows to Bridge source; alert on Studio-authored drift | Engineering | Phase 2 (May 2026) |
| INS-* workflows (insurer notifications) | Charter §4.3 workflows for INS-01..06 | Engineering | Phase 2 (May-Jun 2026) |

7.  Pending Items

| Feature / Workstream | Description | Priority | Remarks |
| --- | --- | --- | --- |
| 32 remaining Charter workflows | OPS-* operations + REG-* regulator + remaining INV/INS | P1 | Phased over 2-3 quarters; ~10 per phase |
| AWS SES provisioning | Email channel — currently skipped at dispatch with SesNotConfigured | P1 | Pending CTO budget approval |
| FCM/APNs push channel | Mobile push to TPE app | P2 | Out of current Charter scope |
| Gupshup SMS fallback | Per Charter strategy: failover Gupshup → MSG91 → Karix | P2 | Risk mitigation for MSG91 single-vendor concentration |
| FCM token + APNs cert provisioning | Required before push integration can be configured | P2 | Engineering + Mobile team coordination |
| Production Track A migration | ECS Fargate multi-AZ migration from VPS pilot | P1 | Charter milestone gate; tied to go-live readiness |
| Hindi locale templates | All 17 Charter workflows currently English-only | P1 | DLT registration + CX-approved copy needed for each |
| Operator training sessions | Walk through Operator Manual with the Ops team | P1 | Schedule after this status doc lands |
| VAPT/security pentest | External security review of sandbox 3.15 stack | P1 | Pre-Track-A migration prerequisite |
| Backup/DR cron testing | Verify backup restore against actual outage scenarios | P2 | Currently set up; not exercised on stage |

8.  Future Roadmap

| Phase | Feature | Timeline | Effort (PD) |
| --- | --- | --- | --- |
| Phase 1.5 | video-kyc-webrtc key rotation + history scrub | 1 week | 3-5 |
| Phase 2 | INS-01..06 insurer workflows | May-Jun 2026 | 20-25 |
| Phase 2 | AWS SES provisioning + email channel live | Jun 2026 | 8-10 |
| Phase 2 | Hindi locale rollout for 17 PH/INV workflows | Jun-Jul 2026 | 15-20 |
| Phase 3 | OPS-01..15 operations workflows | Jul-Aug 2026 | 25-30 |
| Phase 3 | Gupshup SMS fallback wiring | Aug 2026 | 5-8 |
| Phase 3 | FCM/APNs push integration | Aug-Sep 2026 | 10-12 |
| Phase 4 | REG-01..06 regulator workflows | Sep 2026 | 12-15 |
| Phase 4 | Production Track A (ECS Fargate) migration | Sep-Oct 2026 | 30-40 |
| Phase 4 | External VAPT + remediation | Oct 2026 | 10-15 |
| Phase 5 | Go-live readiness review + cutover | Nov 2026 | 8-10 |

9.  Upcoming Deliveries

| Version | Features | Planned Release |
| --- | --- | --- |
| v2.0 (released today) | Sandbox 3.15 primary, Operator Manual, Project Status, Pivot ADR, GitHub repo | 01 May 2026 |
| v2.1 | Drift-check script, MSG91 templates audit, weekly health-check report | 8 May 2026 |
| v2.2 | INS-01..03 workflows + AWS SES provisioning | 29 May 2026 |
| v2.3 | INS-04..06 + Hindi locale for all 17 existing workflows | 26 Jun 2026 |
| v3.0 | OPS-01..15 + Gupshup SMS fallback | Aug 2026 |
| v3.5 | FCM/APNs push + REG-01..06 | Sep 2026 |
| v4.0 | Track A production migration + VAPT remediation | Oct 2026 |
| v5.0 (GA) | All 49 workflows + go-live cutover | Nov-Dec 2026 |

10.  Risks & Dependencies

| Risk | Impact | Mitigation |
| --- | --- | --- |
| video-kyc-webrtc leaked RSA private keys at HEAD on GitHub | 🔴 CRITICAL — GoDaddy *.inadev.net wildcard SSL key + 2 SSH keys publicly committed since Feb 2026 | Phase 1 rotation required this week. Plan documented in memory/vkyc_repo_secret_leak.md. |
| MSG91 single-vendor concentration for SMS | 🟠 HIGH — outage at MSG91 = TPE SMS down. No automatic failover currently. | Phase 3 Gupshup fallback wiring; pre-DLT register templates with backup vendor. |
| Email channel deferred indefinitely | 🟠 HIGH — Charter mandates email + SMS+WA+InApp; deferral = compliance risk for future audit | Provision AWS SES in Phase 2 (Jun 2026); budget approval pending. |
| DLT template change-control process undocumented | 🟠 MEDIUM — adding a new SMS template requires MSG91 portal + compliance lead approval | Document the change-control flow in next charter addendum. |
| Sandbox 3.15 single-VPS deployment (Track B) | 🟠 MEDIUM — single point of failure; no horizontal scaling | Track A production migration (ECS Fargate) in Phase 4. |
| Operations team Novu CE Studio learning curve | 🟢 LOW — operators familiar with old TPE Admin; new dashboard is different | Operator Manual + scheduled training sessions; estimated 1-week ramp. |
| Code-first authoring rule operator-restrictiveness | 🟢 LOW — operators cannot author ad-hoc workflows; every new trigger needs engineering | Acceptable trade-off; revisit after 6 months if operator load is high. |
| 3.x→2.3.0 backport not possible | 🟢 LOW — sandbox 3.15 is forward-only; if we need to roll back to live 2.3.0, must re-author code-first workflows for 2.3.0 SDK | Bridge SDK abstraction softens this; code is mostly forward-compatible (verified). |

11.  Architecture Overview

11.1  Tech stack

| Layer | Technology | Version | Notes |
| --- | --- | --- | --- |
| Frontend (Operator UI) | Novu CE Dashboard | 3.15.0 | Standard React app from upstream |
| API + Worker | Novu CE | 3.15.0 | Self-hosted, sandbox env |
| Custom Bridge | Next.js + @novu/framework | 2.6.x / Next 14 | Code-first workflows in TypeScript |
| Data (sandbox) | MongoDB | 7.x | Single instance per stack |
| Cache / Queue | Redis | 7.x | Job queue for worker |
| S3 stub (sandbox) | LocalStack | — | Sandbox-only; live uses real S3 |
| Reverse proxy | Caddy / nginx | — | TLS termination + sub-path routing |
| VPS | CentOS 9 | — | 103.138.96.180:7576, Mumbai |
| Source control | Git + GitHub | — | github.com/aksatyamtpe/tpe-novu |

11.2  Services + ports (sandbox stack)

| Container | Port (host) | Role |
| --- | --- | --- |
| next-dashboard | 8080 | Operator UI |
| next-api | 8081 | Novu API receiving /v1/events/trigger |
| next-ws | 8083 | WebSocket for in-app Inbox |
| next-worker | (internal) | Job processor |
| next-bridge | (4001 internal) | Custom code-first workflow + dispatch |
| next-mongodb | (internal) | Data store |
| next-redis | (internal) | Job queue |
| next-localstack | (internal) | S3 stub for sandbox |
| next-admin | (internal) | Legacy 3.x admin (auto-launched) |

12.  Security Overview

Compliance posture across DPDPA (India), IRDAI (insurance regulator), and DLT (TRAI SMS):

| India-resident data | ● Mumbai VPS, ap-south-1 region equivalent |
| --- | --- |
| DPDPA — PII isolation | ● Subscriber phone/email never leaves India |
| IRDAI — audit row per dispatch | ● Charter §4.8 compliant; audit emitted from dispatch.ts |
| DLT — SMS template registration | ● 7 templates registered + wired |
| DLT — sender ID | ● TPolEx (TRAI-approved) |
| Compliance middleware lint | ● ≥30 rules in CI gate |
| Secrets in source | ● None in this repo (gitignored *.pem, *.env) |
| Secrets in sister repo (video-kyc-webrtc) | ● 🚨 3 RSA keys leaked since Feb 2026 — open finding |
| STORE_ENCRYPTION_KEY rotation | ● Effectively un-rotatable (Charter §29 special handling) |
| SSH key for VPS | ● id_novu_vps (ED25519, dedicated) |
| Pre-commit secret scan | ● Opsera gate active on this repo |

12.1  Provider compliance posture

| Provider | Compliance status | Audit trail |
| --- | --- | --- |
| MSG91 SMS | DLT-registered + sender ID approved + 7 template_ids live | Per-dispatch audit row with template_id, recipient, status, timestamp |
| ICPaaS WhatsApp | Meta-approved Cloud API + ICPaaS SDK + dynamictemp2 template family | wamid issued per send; audit row + ICPaaS dashboard reconciliation |
| AWS SES Email | Not provisioned — deferred to Phase 2 | Will use VPC endpoint to keep traffic in-region when provisioned |
| Novu Inbox | Self-hosted — no PII leaves the VPS | Activity Feed shows in-app delivery confirmation |

13.  VAPT / Vulnerability Findings

External penetration testing has not been commissioned yet (planned for Phase 4 pre-Track-A migration). Internal security findings as of this document version:

| Finding ID | Severity | Title | Status |
| --- | --- | --- | --- |
| TPE-SEC-2026-001 | 🔴 CRITICAL | Leaked GoDaddy *.inadev.net wildcard SSL private key in video-kyc-webrtc git history | Open — rotation in progress |
| TPE-SEC-2026-002 | 🟠 HIGH | Leaked tpe-stage-ekyc.pem SSH private key in video-kyc-webrtc git history | Open — rotation in progress |
| TPE-SEC-2026-003 | 🟠 HIGH | Leaked tpe-bulk-import.pem SSH private key in video-kyc-webrtc git history | Open — rotation in progress (purpose audit needed) |
| TPE-SEC-2026-004 | 🟡 MEDIUM | Pre-commit Opsera gate only blocks NEW findings — 422 pre-existing findings persist | Mitigation: add gitleaks pre-commit hook with strict policy |
| TPE-SEC-2026-005 | 🟢 LOW | Stale SSH alias `github-personal` in ~/.ssh/config orphaned key not on any account | Cleanup; no exploit path |

VAPT scan timeline External VAPT scheduled for Phase 4 (Oct 2026) as a pre-go-live gate. Internal scans (gitleaks, checkov, semgrep, hadolint, npm audit, grype) run via Opsera plugin on commit but only flag NEW findings. A daily cron-driven full-repo scan is planned for Phase 1.5.

14.  Functional Gaps Summary

Charter §4.3 mandates 49 lifecycle triggers. Current state:

| 17 Live | 0 In progress | 32 Pending | 35% Charter coverage |
| --- | --- | --- | --- |

| Audience group | Charter count | Live | Pending | Phase |
| --- | --- | --- | --- | --- |
| PH (Policyholder) | 17 | 10 | 7 | Phase 2-3 (May-Aug 2026) |
| INV (Investor) | 12 | 7 | 5 | Phase 2 (May-Jun 2026) |
| INS (Insurer) | 6 | 0 | 6 | Phase 2 (May-Jun 2026) |
| OPS (Operations) | 9 | 0 | 9 | Phase 3 (Jul-Aug 2026) |
| REG (Regulator) | 5 | 0 | 5 | Phase 4 (Sep 2026) |
| TOTAL | 49 | 17 | 32 | — |

14.1  Channel coverage

| Channel | Status | Provider | Gap |
| --- | --- | --- | --- |
| SMS | ● Live | MSG91 | Gupshup fallback not wired |
| WhatsApp | ● Live | ICPaaS | None |
| Email | ● Deferred | (AWS SES) | SES not provisioned |
| In-app | ● Live | Novu Inbox | None |
| Push | ● Pending | (FCM/APNs) | Out of Phase 1; Phase 3 target |

15.  Environment Access

15.1  Stage VPS surfaces

| Surface | URL | Access |
| --- | --- | --- |
| Sandbox Dashboard (PRIMARY) | http://103.138.96.180:8080 | sandbox@tpe-test.local / SandboxStage2026! |
| Sandbox API | http://103.138.96.180:8081 | ApiKey 54ad9d4dd50398489413be350237bd88 |
| Sandbox WebSocket | ws://103.138.96.180:8083 | Per-subscriber token |
| Live Dashboard (legacy) | http://103.138.96.180/ | (same dashboard creds) |
| Live API | http://103.138.96.180/api | (legacy ApiKey) |
| TPE Admin (sunsetted) | http://103.138.96.180/admin | DOWN — containers stopped + preserved |
| VPS root SSH | ssh -i ~/.ssh/id_novu_vps -p 7576 root@103.138.96.180 | Engineering + Infrastructure leads only |

15.2  Source code repositories

| Repo | URL | SSH alias for push |
| --- | --- | --- |
| tpe-novu (this project) | github.com/aksatyamtpe/tpe-novu | github-work-tpe |
| video-kyc-webrtc | github.com/Fairvalue-Insuretech/video-kyc-webrtc | github-work |
| tpe-admin (legacy) | github.com/Fairvalue-Insuretech/tpe-admin | github-work |
| tpe-backend | github.com/Fairvalue-Insuretech/tpe-backend | github-work |

16.  Effort Summary

| 3 Commits to date | 1.6K Insertions | 1 Files deleted | 190 Files tracked |
| --- | --- | --- | --- |

| Metric | Value | Notes |
| --- | --- | --- |
| Commits | 3 (initial + README + skills) | On main branch |
| Lines of TypeScript (Bridge) | ~3,500 | Bridge workflows + lib |
| Lines of Python (DOCX generators) | ~3,400 | 5 generators total |
| Lines of markdown (skills + memory) | ~5,200 | 12 skills + memory files |
| Files tracked | 190 | Excludes node_modules, .next, *.pem |
| Total project duration to date | ~3 weeks | From kickoff to v2.0 |
| Engineering effort consumed | ~25 person-days | Across all roles |
| Engineering effort remaining (estimate) | ~120-150 PD | Phase 2 through go-live |

17.  Commit Type Breakdown

Conventional commits since project inception:

| Type | Count | Examples |
| --- | --- | --- |
| docs | 2 | README.md, Operator Manual, Project Status, Pivot ADR |
| feat | 0 | (Workflow code lives in Bridge — sync'd, not committed to this repo yet) |
| fix | 0 | (N/A in this repo; Bridge fixes happen in deployment subtree) |
| chore | 1 | Initial commit: project scaffold + 17 workflows + skills + CLAUDE.md |

Why so few commits This GitHub repo (tpe-novu) was just published on 1 May 2026 with the existing project state as a single initial commit. The 3 weeks of work prior were unversioned (engineering happened directly on the VPS source tree). Future commits will follow conventional-commit format and this section will populate as the project matures.

18.  References & Links

18.1  Source code

| Resource | Link |
| --- | --- |
| Project repo | https://github.com/aksatyamtpe/tpe-novu |
| Novu CE upstream | https://github.com/novuhq/novu |
| Charter (PDF) | docs/TPE_Communication_System_Charter_v1.0.docx |
| Combined Deployment Guide | deployment/Novu-Combined-Deployment-Guide.docx |
| Operator Manual | docs/TPE_Communication_System_Operator_Manual_v1.0.docx |

18.2  Operational docs (in repo)

| Skill / Memory | Path |
| --- | --- |
| Skills index | .claude/skills/INDEX.md |
| sandbox-bridge-recreate | .claude/skills/novu-ce-sandbox-bridge-recreate/ |
| pivot-rollback | .claude/skills/novu-ce-pivot-rollback/ |
| bridge-sync | .claude/skills/novu-ce-bridge-sync/ |
| smoke-test | .claude/skills/novu-ce-smoke-test/ |
| upgrade | .claude/skills/novu-ce-upgrade/ |
| troubleshoot | .claude/skills/novu-ce-troubleshoot/ |

18.3  Stakeholder dashboards

| Resource | URL |
| --- | --- |
| Sandbox Dashboard (operator UI) | http://103.138.96.180:8080 |
| Sandbox API | http://103.138.96.180:8081 |
| MSG91 portal (DLT + delivery) | https://control.msg91.com/ |
| ICPaaS dashboard (WA delivery) | http://www.icpaas.in/ |
| GoDaddy (SSL cert mgmt) | https://godaddy.com/ → My Products → SSL |

Prepared by Ashish Kumar Satyam TechDigital WishTree · for The Policy Exchange Internal / Confidential